## Sheet1
				Table of projects of pan - European significance

Project identification					Project assessment					Present status	Expected date of commissioning	Evolution compared to the TYNDP 2010 situation	Investment comment	Project comment
Project number	Investment number	Substation 1	Substation 2	Brief technical description	Grid Transfer Capability Increase [MW]	Socio-economic Welfare	RES integration	Improved Security of Supply	Losses variation	CO2 mitigation	Technical resilience	Flexibility	Social and environmental Impact	Project costs		Expected date of comissioning

1	1. 1	Frades B (PT)	Pedralva 1&2 (PT)	Creation of a new 400kV station in Frades B connected to Pedralva by means of two new 400kV, 40km lines. The realisation of this two connections can take advantage of some already existing 150kV single lines, which will be reconstructed as double circuit lines 400+150kV line and partially sharing towers with those 400kV circuits.	3800	4	1	Tras -os Montes and the Alto Duore area					2	design & permitting	2014	Adjustment resulting from the new date of the hydro power plant.		This project integrates new amounts of Hydro Power Plants in the Northern region of Portugal (3200 MW of which 2700 MW with pumping) and to create better conditions to evacuate Wind Power already existent and new with authorization for connection. These new amounts of power will increase the flows in the region, and it is estimated that the flows could reach 3800 MW, which must be evacuated to the littoral strip and south Portugal through three new independent routes. Part of these flows will interfere and accumulate with the already existent flows entering in Portugal through the international interconnections with Spain on the North, the Alto Lindoso-Riba de Ave-Recarei and Lagoaça-Aldeadávila axis, which induces additional needs for reinforcement of this axis in a coordinated way.
1	1. 2	Pedralva (PT)	Alfena (PT)	New 50km double circuit Pedralva (PT) - Alfena (PT) 400kV OHL, (only one circuit installed in a first step). This line is going to use partially a corridor of a existing single 150 OHL.					planned	2017	Adjustment resulting from the new date of the hydro power plant.		1
1	1. 3	Pedralva (PT)	Vila Fria (PT)	New 55km double circuit Pedralva - Vila Fria 400kV OHL (one circuit installed), with needed extension of existing Vila Fria substation to include 400kV facilities.					design & permitting	2014/2015	Delays due to authorization process.		1
1	1. 4	Frades B - Ribeira de Pena - Feira (PT)	0	New 160km double-circuit 400kV OHL Frades B (PT) -Ribeira de Pena (PT) - Feira (PT) (one circuit operated at 220kV between R. Pena and Feira) with a new 400/60kV substation in Rib. Pena. In a first step, only the 130km section Rib. de Pena (PT) - Feira (PT) will be constructed and operated at 220kV as Vila Pouca Aguiar (PT) - Carrapatelo (PT) - Estarreja (PT) (see project 6). In a second step, one circuit of this line will be operated at 400kV.					design & permitting	2015/2016	Progresses as planned		1
1	1. 5	Macedo de Cavaleiros (PT)	Vila Pouca de Aguiar (PT)	New 75km double circuit 400+220kV OHL Macedo de Cavaleiros (PT) -Valpaços (PT) - Vila Pouca de Aguiar (PT).					partly under construction, design & permitting	2011/2012	Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.Delays due to authorization process. / A section of the line Macedo de Cavaleiro-Vila Pouca de Aguiar between Macedo de Cavaleiros and Valpaços (53 km) was commissioned at the end of 2011.	This project allows the connection of RES (mainly wind) and increases the trasnmission capacity in the Douro area.	1
1	1. 6	V. P. Aguiar - Carrapatelo - Estarreja (PT)	0	New 400+220kV double circuit OHL (initially only used at 220kV) Vila Pouca Aguiar - (Rib. Pena) - Carrapatelo - Estarreja . Total length of line: 2x(90+49)km.					design & permitting	2013	Delays due to authorization process.	This project allows the connection of the RES (mainly wind) and new load in the area.	1
1	1. A1	Ribeira de Pena - Guarda (PT)	0	New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT). / New 192km double/single-circuit 400kV OHL Ribeira de Pena (PT) - Guarda (PT). / In a first step, only the 75 km section Ribeira de Pena - Guarda will be constructed and operated at 220 kV between Vila Pouca de Aguiar and Macedo de Cavaleiros (see project 5), in a second step one circuit of this line will be operated at 400 kV. Between Macedo de Cavaleiros zone and Pocinho zone a single line will be constructed, between Pocinho zone and Chafariz zone a double circuit 400 kV OHL will be constructed (only one circuit installed in a first step), this last line will use one circuit of the line V. Chã B - Guarda (see project New PT 1) to establish the line Ribeira de Pena (PT) - Guarda (PT).					planned	2022	New investment in TYNDP. This investment the supports the integration of new hydro and wind power plant in Northern Portugal		1
2	2. 8	V. Chã B - Arg./Góis - Penela - Paraimo / Batalha (PT)	0	New single circuit 400kV OHL Vila Chã B-Arganil/Gois-Penela (90km) plus new double circuit 400kV OHL (15km) to connect Penela substation to Paraimo - Batalha line. Two new 400/60kV substations at Vila Chã B and Arg./Góis are needed, as well as the expansion of the existing Penela substation to include 400kV facilities.	1800	4	1					2	design & permitting	2015/2016	Progresses as planned		This project integrates new hydro power plants (590 MW with pumping) and evacuates the existent and new wind generation in the inner central region of Portugal (it is expected to connect more 800 MW of new wind, but the wind target in this region overcomes surmounts of more than 2000 MW). The existing network of 220 kV and 150kV is no more adequate to integrate these new amounts of power, and a new 400kV axis should be launched in this region in a two major routes: one to the littoral strip (Penela/Paraimo/Batalha) and another by the interior, establishing a connection to Falagueira substation, where there is an interconnection with Spain (Falagueira-Cedillo).
2	2. 9	Guarda - Ferro B - (C. Branco) - Falagueira (PT)	0	New double circuit 400+220kV OHL Guarda (PT) -Ferro B (PT) -'Castelo Branco zone' (PT) (between Guarda and Ferro B only the 400kV circuit will be installed) plus new double circuit 400+150kV OHL 'Castelo Branco zone' (PT) -Falagueira (PT). New 400/60kV substations in Guarda and Ferro B. Total length of line: 135km.					design & permitting	2015/2016	Adjustment resulting from the new date of the renewables project.		2
2	2. 10	Falagueira (PT)	Pego (PT)	New 40km double circuit 400+150kV OHL substituting for an existing 150kV line.					design & permitting	2014	Progresses as planned		2
2	2. A2	V. Chã B - Guarda (PT)	0	New double circuit 400kV OHL Vila Chã B-Guarda (55km)					planned	2020	New investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern PortugalNew investment in TYNDP / This investment supports the integration of new hydro and wind power plant in Northern Portugal		2
3	3. 12	Rio Maior - Alm. Bispo - Fanhões (PT)	0	New 71km double circuit 400kV OHL feeding Lisbon area from north with creation of a 400/220/60kV substation in Almargem do Bispo. A section of this reinforcement (between Rio Maior and Carvoeira zone) will be finished earlier included on a 400/220kV double circuit line linking Rio Maior and Carregado substations.	1880	2	5	Lisboa and Setúbal Peninsula					1	planned	2016/2019	Progresses as planned		This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads. / This project reinforceS the security of supply of Lisbon and Setubal region (north and south Tagus river) by creating a strong semi-ring of 400 kV, with two new 400kV substations that can guarantee the load growth in the region in a safe, secure and quality way. / Currently there are only 3 400/VHV substations (Alto de Mira, Fanhões and Palmela), and two of them are quite far from the main load. This new project will create two new 400 kV substations near the main loads.
3	3. 13	Palmela - F. Ferro -Ribatejo (PT)	0	Expansion of Fernão Ferro substation to include 400kV facilities and connection to the existent Palmela (PT) - Ribatejo (PT) single circuit line by a new 25km double-circuit 400kV OHL.					under construction	2012	Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.Progresses as planned / Line Palmela-F.Ferro-Ribatejo was commisined at the end of 2011. / The expansion of Fernão Ferro substation to include the 400 kV will be concluded only in 2012.		3
3	3. 14	Marateca - Pegões - Fanhões (PT)	0	New 400/60kV substations in Pegoes. New 90km double-circuit 400kV OHL . This new line will be connected to already existing line Palmela (PT) - Sines 2 (PT) , so making a direct link Sines-Pegões (PT) -Fanhões (PT) substations.					under construction	2012	Progresses as planned		3
4	4. 16	Aldeadávila (ES)	Lagoaça (PT) - Armamar (PT) - Recarei (PT)	New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).New Duero Interconnection 400kV / New 400kV OHL interconnection line Aldeadávila (ES) - Lagoaça (PT) , including new Lagoaça substation (PT). Also associated, the lines Lagoaça-Armamar-Recarei 400kV in PT and the Armamar (PT) 400/220kV substation. / On a first phase (2009) a new 400/220kV substation (Lagoaça - PT) will be created with only 220kV level installed, and there will be some rearrangements and reinforcements on the local 220kV network structure. On river crossing a new 220kV double line with separated circuits, firstly Aldeadavila (ES) - Lagoaça (PT) 1 & 2 and changing later to Aldeadavila (ES) - Pocinho (PT) 1 & 2, will substitute the existing two 220kV lines Aldeadavila (ES) – Bemposta (PT) and Aldeadavila (ES)-Pocinho (PT). Total length: 1km (ES)+105km (PT).	P>E 1700 - E>P 1400	3	2					2	partly completed, design & permitting	Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.Aldeadavila-Lagoaça 400kV (cros border ), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV commissioned in 2010. / Armamar (PT)-Recarei (PT) expected in 2012.	Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.Aldeadavila-Lagoaça 400kV (cross-border), Aldeadavila (ES) - Pocinho (PT) 1 & 2 220 kV, Lagoaça 400/220 kV Substation, Armamar (PT)-Lagoaça (PT) 400 kV completed. / Portuguese section Armamar (PT)-Recarei (PT) delayed in autorization process.		This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" . This project increases the capacity between PT and ES. Larger and more volatile flows are expected between both countries due to the huge increase of volatible sources and the market interchanges. / The project includes two interconnection routes, besides the internal reinforcements required, one in the North and other in the South, due to the important loop flows between the two countries and, consequently, only both interconnections allow to reach a reasonable import/export capacities that will reach the "3.2 GW" .
4	4. 17	Guillena (ES)-Puebla de Guzman (ES)	Tavira (PT)-Portimao (PT)	New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).New Southern Interconnection / New 400kV OHL double-circuit line between Guillena (ES)-Puebla de Guzman (ES) - Tavira (PT) - Portimão (PT), including new Tavira (PT) and P.Guzman (ES) 400kV substations. On the interconnection section P.Guzmán (ES) –Tavira (PT), initially only one circuit will be placed. Total length: 25km (ES)+110km(PT).	P>E 1700 - E>P 1400					partly under construction, design & permitting	2012-2013	Portuguese section commissioned.P. Guzman -Guillena (ES) built and operating at 220kV. Difficulties in the authorization process in the Spanish section P. Guzman - border and connection to Guillena 400 Kv.		4
4	4. 18	Boboras (ES)-O Covelo (ES)	Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)Vila Fría (PT)- / Vila Conde (PT) - Recarei (PT)	New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT). New northern interconnection. New double circuit 400kV OHL between O Boboras (ES) -O Covelo (ES) - Vila Fria (PT) - Vila do Conde (PT) - Recarei (PT), including new 400kV substations O Covelo (ES), Boboras (ES), Vila Fria (PT) and Vila do Conde (PT). / On the section O Covelo (ES) – Vila do Conde (PT), only one circuit will be placed. Total length: 50km (ES)+112km (PT).	P>E 1700 - E>P 1400					design & permitting	2014	Progresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraintsProgresses as planned. / Changes in route and connecting point in Spain due to environmental constraints		4
4	4. 21	Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)Aldeadavila (ES) / JM Oriol (ES)	Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES) Villarino (ES) / Caceres (ES)	Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV / Uprating the existing Aldeadávila-Villarino 400kV OHL in order to increase its capacity from 1350MVA to 1690MVA. / Uprating the existing line JM Oriol-Caceres 220 kV					under construction	2013	Progress ans planned, altough there are difficulties to find a suitable period for a planned outage to carry on the project.		4
4	4. 21	JM Oriol (ES)	Arenales -Caceres (ES)	New 220kV JM Oriol-Arenales, and new Arenales substation.	P>E 1700 - E>P 1400					design & permitting	2014	Delays due to authorization process.		4
5	5. 19	Vic (ES)	Pierola (ES)	Upgrading (uprating) the existing 75km single circuit Vic-Pierola 400kV line in order to increase its capacity from 1360 MVA to 1710 MVA.	1200-1400 in both directions	1	2	Perpignan, Gerona					2	under construction	2012	Delays due to authorization process.		Mid-term interconnection project between France and Spain ("2.8 GW") . It includes cross border lines and internal lines required to assure NTC.
5	5. 20	Arkale (ES)	Hernani (ES)	Upgrading the existing single circuit Arkale-Hernani n°2 220kV OHL in order to increase its capacity up to 640 MVA.					design & permitting	2014	Delays due to authorization process.		5
5	5. 36	Sta.Llogaia (ES)	Baixas (FR)	New HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors and converters in both ending points.					partly under construction, design & permitting	2014	Progresses as planned.		5
5	5. 37	Santa Llogaia (ES)	Bescanó (ES)	New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.New double circuit Sta.Llogaia-Ramis-Bescano-Vic/ Senmenat 400kV OHL (single circuit in some sections) / New 400kV substations in Bescano, Ramis and Sta.Llogaia, with 400/220kV transformers in Ramis and Bescano.					under construction	2011-2013	Bescano-Vic/Senmenat 400 KV commissioned. Difficulties in the authorization process of the section Bescano-Sta Llogaia 400kV		5
5	5. 46	Baixas (FR)	Gaudière (FR)	Reconductoring of existing 70km double circuit 400kV OHL to increase its capacity.					design & permitting	end 2013	Progresses as planned		5
6	6. 22	Boimente (ES)	Grado (ES)	North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV. / North axis Project between Galicia and the Basque Country. / Part of the project is considered as the Asturias Ring. / New double circuit Boimente-Pesoz-El Palo-Salas Grado 400kV OHL. / Change of voltage level of the existing Soto-Tabiella single circuit from 220kV to 400kV, and connection as input/output in Grado. / New single circuit Soto-Penagos 400kV OHL. / New double circuit Aguayo/Penagos-Udalla-Abanto 400kV OHL / New double circuit Zierbena-Abanto-Gueñes 400kV OHL. / New double circuit Gueñes-Ichaso OHL. / New double circuit Gozón-Reboria--Sama-Lada 400kV OHL. / New double circuit Sama-Velilla 400kV OHL. / Uuprating the single circuit Lada-Robla 400kV OHL in order to increase its capacity by around 300 MVA. / It includes new 400kV substations Pesoz, El Palo,Salas, Grado, Gozón, Sama, Reboria , Costa Verde, Penagos, Solorzano, Udalla, Abanto and several transformers to 220kV.	2000- 4200	5	2					2	partly completed, design & permitting	2012-2014	Section Pesoz-Salas commissioned. El Palo connection is in progress. Difficulties in the authorization process of the section Boimente-Pesoz and Salas-Grado		Larger and more volatile West East power flows from Galicia to the Basque Country, triggered especially by the developement of new generation sources in the North and North Western part of the country (mainly wind, a new pumping hydro power plant, and some CCGT that will replace former coal power plants) and the need to feed the high industrial and demanding regions of the North and NorthEastern part of Spain.
6	6. 22	Soto -Grado- Gozon-Reboria (ES)	Costaverde-Sama (ES)					design & permitting	2015	Changes in the definition of the investment: Subestation Valle del Nalón 400kV is not required as the link can not take advantage of existing 132kV due to technical and environmental problems, conection Gozón-Carrio 400kV can not use existing corridor of lower voltage lines and requires therefore a new subestation Reboria 400kV.		6
6	6. 22	Soto (ES)	Penagos (ES)					completed	commissioned	Commissioned		6
6	6. 22	Sama (ES)	Velilla (ES)					design & permitting	2015	Delays due to authorization process.		6
6	6. 22	Lada (ES)	Robla (ES					completed	commissioned	Commissioned		6
6	6. 22	Penagos/Aguayo (ES)	Abanto (ES)					partly completed, design & permitting	2012	From Penagos/Aguayo to udalla commissioned. The connection from udalla to Abanto has delays in authorisation process		6
6	6. 22	Zierbena (ES)	Abanto (ES)					completed	commissioned	Commissioned		6
6	6. 22	Abanto/Gueñes (ES)	Ichaso (ES)					design & permitting	2016	Delays due to authorization process.		6
7	7. 23	Ichaso (ES)	Castejón (ES)	Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service / Northern part of the new Cantabric-Mediterranean axis. New double circuit Castejón-Muruarte-Dicastillo-Ichaso 400kV OHL, with new 400kV substations in Muruarte and Dicastillo with 400/220kV transformers.Section Castejón-Muruarte 400kV already in service	1320--4280	1	1					2	partly completed, design & permitting	2017	Castejón-Muruarte section have been commisioned. Muruarte-Dicastillo-Ichaso has difficulties in the authorisation process which led to change the route and connection (Ichaso substitutes Vitoria)		Larger and more volatile Cantabric-Mediterranean power flows in Spain, triggered by the development of local RES but also influenced by transits flows caused by the generation/demand situations in the North and Levante areas.
7	7. 23	La Serna (ES)	Magallón (ES)	New double circuit La Serna-Magallón 400kV OHL.					design & permitting	2014	Delays due to authorization process.		7
7	7. A4	Tudela (ES)	Magallón (ES)	New CCRS (Combination of Reactors step by step) in Magalló 220 kV					design & permitting	2013	New investment in the TYNDP, as it is required to ensure the GTC increase for the entire project		7
7	7. A5	Dicastillo (ES)	Moncayo (ES)	New double circuit Dicastillo-El Sequero-Santa Engracia-Magaña-Moncayo 220kV OHL.					design & permitting	2013-2017	New investment in the TYNDP. Ensures the GTC increase of the project while helping to evacuate the generation in Soria and Aragón.		7
7	7. 23	Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES) / Aragón (ES) / Tudela (ES) / La Serna (ES)	Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)Peñaflor (ES) / Magallón (ES) / Ichaso (ES)	Uprating the existing Aragón-Peñaflor 400kV OHL , Tudela-Magallón 220kV and La Serna-Ichaso 220 kV.					design & permitting	2013-2014	New investment in the TYNDP. Difficulties in the authorization process		7
7	7. 24	Fuendetodos /Mudejar (ES)	Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)Eliana/ / Godelleta(ES)	Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units / Southern part of the new Cantabric-Mediterranean axis. / New double circuit Fuendetodos-Muniesa-Mezquita-Platea-Godelleta 400kV OHL. / New double circuit Teruel-Mudejar-Morella-la Plana/Godelleta 400kV-OHL. / the new TGodelleta substation will be equipped with a 400/220kV transformer and connected to the existing 400kV lines Cofrentes-La Eliana, and Catadau-Requena 400kV lines. / New 400kV substations Mezquita, Platea, Muniesa, Mudejar and Godelleta with 400/220kV transformer units					design & permitting	2012-2015	Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015Turis subestation is substituted by Godelleta due to environmental reasons. / Uprate Eliana-La Plana and new circuit is rejected due to environmental reason. As alternative a double circuit connection morella-Godelleta/La plana. / These issues delay the project up to 2015		7
8	8. 25	Aragón (ES)	Isona (ES)	New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero. / New double circuit Aragón/Peñalba-Arnero-Isona 400kV OHL with new 400kV substations Arnero and Isona, and a 400/220kV transformer in Arnero.	3870	1	3					1	design & permitting	2014	Delays due to authorization process.. In addition, Monzón subestation is substituted by Arnero		Larger and more volatile South- NorthEastern power flows from Aragón to Catalunya, triggered especially by the developement of new RES in the south of Catalunya and Aragón, that joined to the existing generation sources (RES and conventional) in this area andfurther in the south causes higher flows, that would naturally flow to the large consumption areas in Catalunya.
8	8. 25	Escatron (ES)	La Secuita (ES)	New single circuit Escatrón-Els Aubals-La Secuita 400kV OHL with new 400kV substation in Els Aubals and La Secuita with 400/220kV transformer.					design & permitting	2015	Delays due to authorization process.		8
8	8. A6	Torres del Segre(ES)	Mequinenza (ES)	New SSSC (Static Synchronous Series Compensator) in Torres del Segre-Mequinenza 220kV.					design & permitting	2013	New investment in the TYNDP. Ensures the GTC increase of the project while alleviating present and the future congestion in the parallel 220kV axis		8
8	8. A7	Mangraners (ES)	Begues (ES)	New Double circuit Mangraners-Espluga-Begues and Mangraners-Juneda-Secuita-Perafort-Begues 220 kV					design & permitting	2013	New investment in the TYNDP. Ensures the GTC increase of the project while alleviating present and the future congestion in the parallel 220kV axis		8
8	8. A8	Espluga (ES)	Penedes (ES)	Uprate 116km single circuit 220kV OHL					design & permitting	2011-2013	New investment in the TYNDP. Ensures the GTC increase of the project while alleviating present and the future congestion in the parallel 220kV axis		8
8	8. A9	Garraf (ES)	Vandellos (ES)	Uprate 108km single circuit 400kV OHL					design & permitting	2015	New investment in the TYNDP. Ensures the GTC increase of the project while alleviating present and the future congestion in the parallel 220kV axis		8
8	8. A10	Isona (ES)	Calders (ES)	uprate 79km single circuit 400kV OHL					design & permitting	2015	New investment in the TYNDP. Ensures the GTC increase of the project while alleviating present and the future congestion in the parallel 220kV axis		8
9	9. 26	Catadau (ES)	Benajama (ES)	New double-circuit Catadau-Jijona-Benejama 400kV OHL .A new 400kV substation will be created at Jijona and transformers installed in Jijona and Catadau.	1840	2	5	Costablanca area					1	design & permitting	2017	Delays due to authorization process.		Security of supply of the Costablanca area in Levante mediterranean coast
9	9. 26	Catadau (ES)	Jijona (ES)	220 kV lines from Catadau to Jijona in the coast of Costablanca using partially the 132KV lines					design & permitting	2016-2019	New investment in the TYNDP complementing the previous one to alleviate congestion in the 132kV lines that supplies Casabanca area. 132 kV lines will be upgraded to 220KV.		9
10	10. 28	Cofrentes (ES)	Ayora (ES)	New single circuit Cofrentes-Ayora 400kV OHL.	3380-4270	4	1					1	design & permitting	2015	Delays due to authorization process. forcing to reschedule the investment		Larger and more volatile East-West flows triggered mainly due to new RES generation development in Valencia, Albacete and Ciudad Real .
10	10. 28	Ayora (ES)	Pinilla (ES)	New single circuit Cofrentes-Ayora-Campanario-Pinilla 400kV OHL. This project also includes a new 400kV substation in Campanario.					design & permitting	2012-2013	Progresses globally as planned		10
10	10. 33	Romica (ES)	Manzanares (ES)	Transmanchega project New double circuit line Romica-Manzanares 400kV OHL. New substation Manzanares with a 400/220kV transformer unit.					design & permitting	2016	Postponed in new national Master Plan as need is not imminent		10
10	10. 33	Manzanares (ES)	Brazatortas (ES)	Transmanchega project New double circuit line Manzanares-Brazatortas 400kV OHL. The new 400kV substation Brazatortas will be connected to the existing line Guadame-Valdecaballeros.					design & permitting	2013	Progresses as planned		10
11	11. 29	Cartuja (ES)	Guadame (ES)	New double circuit Cartuja-Arcos de la Frontera-La Roda-Cabra-Cordoba-Guadame 400kV OHL (partly already commissioned) . It includes new 400kV substations Cartuja and Cordoba, with 400/220kV transformers.	1270	4	1					1	partly completed, design & permitting	2011/2014	Arcos-Cabra-Guadame section commissioned. Cordoba connection postponed in new National Master Plan as need for demand is not imminent. Cartuja-Arcos faces difficulties in the authorization process.		Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North. / Larger and more volatile South-North power flows, triggered especially by the developement of new RES in Cadiz, that joined to the existing generation sources (RES and conventional) in the area causes higher flows, that would naturally flow to the large consumption areas in the North.
11	11. A11	Cartuja-Pto Sta Maria (ES)	Facinas (ES)	New 52km single circuit 220 kV OHL Puerto Sta Maria-Pto.Real-Parralejo-Facinas					design & permitting	2012/2013	New investment in the TYNDP, contributing also to evacuate the generation in the coast of Cadiz		15
12	12. 30	Don Rodrigo (ES)	Aznalcollar (ES)	New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss. New double circuit 400kV OHL: Aznalcollar-Guadaira-Don Rodrigo. Aznalcollar substation will also have a new input/output in Guillena-Palos 400kV. / This project also includes new 400kV substations in Aznalcollar and Guadaira with 400/220kV transformerss.	2150-1600	3	4					2	design & permitting	2017	Delays due to authorization process. which led that Guillena-Guadaira connection is substituted by Aznalcollar-Guadaira with a new topology.		Larger and more volatile Southwestern-Northwestern power flows, triggered especially by the developement of new generation sources in Sevilla and Huelva (mainly wind and solar), but also in Extremadura, that joined to the existing generation sources in the area causes higher flows, that would naturally flow to the large consumption areas in the South (Sevilla) or in the North (towards Madrid), depending on the demand/generation situation.
12	12. 30	Guillena (ES)	Almaraz (ES)	New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss. New double circuit 400kV OHL Guillena-Brovales-Arroyo S.Servan-Carmonita- Almaraz. / This project also includes new 400kV substations in Arroyo S.Servan, Carmonita with 400/220kV transformerss.					design & permitting	2012	Alcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwiseAlcuescar subestation substited by Carmonita. / Progresses as planned otherwise		12
13	13. 31	Caparacena (ES)	La Ribina (ES)	New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). / New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ).	1950-3400	4	1					1	design & permitting	2016	Delays due to authorization process.		The project aims at ensuring the connection to the transmission network of new RES (wind, solar and pumping hydro) and ensuring the possibility of more volatile power flows between the Almeria and Granada.
13	13. 31	Caparacena (ES)	Litoral (ES)	The existing single circuit Litoral-Tabernas-Hueneja-Caparacena 400kV line will be uprated in order to increase its capacity .					under construction	2012	Final phase of permitting.. Progress as planned although there are difficulties to find a suitable period for a planned outages to carry out the work		13
14	14. 34	Trives (ES)	Tordesillas (ES)	New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida, / New line Trives-Aparecida-Arbillera-Tordesillas 400kV OHL and Trives-Conso-Valparaiso-Tordesillas 220kV OHL. New 400kV substations in Aparecida,	600+3000	1	2					2	under construction	2011-2012	Progress as planned. Trives-Tordesillas 400kV axis shares towers with the Trives-Tordesilla 220kV line. Final phase of permitting.		Larger and more volatile Northwestern- Centre power flows , triggered especially by the developement of new RES in Galicia and Castilla-León, that joined to the existing generation sources (RES and conventional) in the area and further in the north causes higher flows, that would naturally flow to the large consumption areas in the centre of Spain, mainly Madrid.
14	14. 34	Tordesillas (ES)	La Cereal /Moraleja (ES)	New double circuit Tordesillas-Segovia- Galapagar 400kV OHL.					under construction	2012-2013	Partly commissioned. Progresses as planned		14
14	14. 34	Segovia (ES)-PST Galapagar	Moraleja (ES)	New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja. / New input/output of Moraleja in Segovia-Galapagar 400kV OHL and new PST in the 400kV line Galapagar-Moraleja.					design & permitting	2013-2015	Delays due to authorization process.		14
14	14. 34	Loeches (ES)	SSReyes (ES)	Upgrade of the existing 21km single circuit Loeches-SS Reyes 220kV OHL to 400kV in order to increase its capacity.					design & permitting	2015	Delays due to authorization process.		14
14	14. 34	Fuencarral (ES)	Galapagar (ES)	Uprate Galapagar-Fuencarral 400kV					design & permitting	2014	New investment in TYNDP		14
14	14. 34	Mudarra (ES)	Tordesillas (ES)	New double circuit 400kV Mudarra-Tordesillas OHL and upgrade of the existing single-circuit Mudarra-Tordesillas 400kV line in order to increase its capacity.					partly under construction, design & permitting	2018	Uprate fostered because of neccesity. New line postponed in new Master Plan.		14
15	15. A12	Olmedilla (ES)	Valdemingomez (ES)	New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco / New double circuit Olmedilla-Villares-Morata-Valdemingomez 400kV OHL, and New substation Villares and Valdemingomez 400kV, with 400/220 kV transformers in T.Velasco	8700	5	1					1	design & permitting	2016/2017	New investment in TYNDP		Larger and more volatile South- Centre power flows , triggered especially by the developement of new RES in Cuenca, that would naturally flow to the large consumption area of Madrid but also influenced by transits flows caused by higher flows coming from the south of Spain.
15	15. 32	(Castilla) (ES)	(Madrid) (ES)	Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV / Uprate Cofrentes-Minglanilla-Belinchon-Morata 400kV,double circuit Trillo-Villanueva Escuderos-Olmedilla-Belinchon 400kV, double circuit Valdecaballeros-Arañuelo 400 kV, double circuit Morata-Villamiel-Almaraz 400 kV, double circuit Villaviciosa- Almaraz 400 kV, double circuit Aldeadavila-Arañuelo and Aldeadavila- Hinojosa-Almaraz 400kV, Picon-Aceca-Los Pradillos-Torrejon de Velasco and Añover-Torrejón de Velasco-Pinto Ayuden-El Hornillo-Villaverde 220 kV					partly under construction, design & permitting	2011/2018	Some of the investments progressed as planned. Other have problems either in permittign process or finding a suitable period for a planned outage to carry out the works.		15
16	16. 38	Gatica (ES)	Aquitaine (FR)	New HVDC (VSC) bipolar interconnection in the Western part of the border, via 320kV DC submarine cable in the Biscay Gulf	Fr->Es 1200 ; Es ->Fr 2000	1	2	Biarritz, Basque country					3	under consideration	ca. 2020	New investment in TYNDP, defined since last release, aiming 4 GW capacity between France and Spain.		Long-term interconnection project between France and Spain ("4 GW") . It includes cross border lines and internal lines required to assure NTC.
16	16. A14	Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)Amorebieta (ES) / Garraf (ES) / Adrall (ES) / Orcoyen (ES)	Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)Gueñes (ES) / Secuita (ES) / La Pobla (ES) / Elgea (ES)	Uprates required in basque country and Catalonia in order to use fully the benefit of the longterm ES-FR interconnection.					under consideration	2016	New investment in TYNDP meant to solve congestion in this area.		16
16	16. A17	Arkale (ES)	0	New PST on Arkale-Argia 220 kV interconnection line					design & permitting	2016	New investment enabling to take full advantage of the transfer capacity of the new subsea interconnection.		16
17	17. 42	Lonny (FR)	Vesle (FR)	Reconstruction of the existing 70km single circuit 400kV OHL as double circuit OHL.	9000	1	2	Reims, Paris area					3	design & permitting	>2019	Progresses as planned		Larger and more volatile North South power flows from Normandy to Champagne, triggered especially by the developement of new generation sources (along the Channel coasts, from Picardie to Champagne and further North abroad) that would naturally flow to large consumption areas: Paris area, but also more broadly from Britanny to Reims.
17	17. 44	Havre (FR)	Rougemontier (FR)	Reconductoring of existing 54km double circuit 400kV OHL to increase its capacity.					design & permitting	2018	As the pace of generation installation is lower than expected, the investment has been postponed.	This investment is needed for integrating new generation in Le Havre area. As the pace of generation installation is lower than assumed earlier, the investment has been postponed from 2015 to 2018	17
17	17. A18	tbd (FR)	tbd (FR)	New network reinforcement between Haute Normandie and the south of Paris area. Length about 160 km.					under consideration	ca. 2020	New investment in TYNDP, defined since last release	Either existing assets uprate or new HVDC, actual needs still being evaluated, depending on uncertainties on generation location	17
17	17. 45	Taute (FR)	Oudon (FR)	"Cotentin-Maine "Project : new 163km double circuit 400kV OHL connected to existing network via two new substations in Cotentin and Maine regions.					under construction	end 2012-beginning 2013	Delays due to authorization process.		17
17	17. A144	Cergy (FR)	Terrier (FR)	MORP project : new single circuit 400-kV underground line between existing 400-kV substations					planned	2018	New investment in TYNDP, defined since last release, triggered by larger and more volatile power flows between generation developping North to Paris and Paris area.		17
18	18. 48	Gaudière (FR)	Rueyres (FR)	Reconductoring with ACCS limiting section (10km) of existing single circuit 400kV OHL.	>1000	3	5	Provence area					3	under construction	end 2012	Progresses as planned		Larger and more volatile North South power flows in South-Western France, triggered by the development of local RES generation but also influenced by transits flows with neighbouring countries.
18	18. A19	tbd (FR)	tbd (FR)	Rectructuration of whole EHV grid in Massif Central area					under consideration	long term	New investment in TYNDP, defined since last release, triggered by larger and more volatile power flows in South West France.		18
18	18. A20	(Provence) (FR)	(Midi) (FR)	New subsea HVDC link beetween Marseille area and Languedoc					planned	2019	New investment in TYNDP, defined since last release, triggered by larger and more volatile power flows in South West France.		18
19	19. 51	Boutre (FR)	La Bocca (FR)	PACA "Filet de sécurité" project: construction of 3 new 220kV underground cables (Boutre - Trans [72 km], Biançon - Fréjus [26 km] & Biançon - La Bocca [16 km]) and installation of reactive power compensation devices in 220 kV Boutre and Trans substations	500	2	5	French riviera					1	design & permitting	2015	Progresses as planned		Security of supply of the French riviera
20	20. 53	Coulange (FR)	Le Chaffard (FR)	Reconductoring (with ACCS / ACCR) of two existing double circuit 400kV OHL (Coulange - Pivoz-Cordier - Le Chaffard and Coulange - Beaumont-Monteux - Le Chaffard). Total length of both lines: 275km	2400	1	5	South East France					2	under construction	2016	Progresses as planned	Construction over 4 years because the works are only possible during limited periods every years on this strategic corridor	The project aims at ensuring the reliable grid operation to cope with new generation developement along the Rhone Valley and more volatile power flows between the Alps and South Western France.
20	20. 18, A20	0	0	0					0	0	0	The investment contributes both to project 18 and project 20. For the technical description see project 18	20
21	21. 54	Cornier (FR)	Piossasco (IT)	Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km) / Replacement of conductors (by ACCS) on Albertville (FR) - Montagny (FR) - Cornier (FR) and Albertville (FR) - La Coche (FR) - La Praz (FR) - Villarodin (FR) - Venaus (IT) - Piossasco (IT) single circuit 400kV OHLs. In addition, change of conductors and operation at 400kV of an existing single circuit OHL between Grande Ile and Albertville (FR) currently operated at lower voltage, and associated works in Albertville (FR) 400kV substation. (Total length of lines : 257 km)	1600 from FR to IT, (600 in the MT)	1	5					3	under construction	2012	Progresses as planned		Planned France-Italy interconnection development
21	21. 55	Grande Ile (FR)	Piossasco (IT)	"Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way."Savoie - Piémont" Project : / New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way.					design & permitting	2017	Progresses as planned		21
21	21. 81	Trino (IT)	Lacchiarella (IT)	A new 380kV double circuit OHL between the existing 380kV substations of Trino and Lacchiarella in North West Italy area. Total line length: 95km, Voltage upgrade of the existing Magenta 220/132kV substation up to 380kV.					under construction	2013	Authorization process ended, construction phase on going		21
21	21. 84	Casanova (IT)	Vignole (IT)	Voltage upgrade of the existing 100km Casanova-Vignole 220kV OHL to 400kV and new 400/220/150kV substation in Asti area.					design & permitting	long term	Delays due to authorization process.		21
21	21. 101	Turin (IT)	0	Restructuring of the 220kV network in the urban area of Turin. Some new 220kV cables, some new 220/132kV substations and some reinforcements of existing assets are planned. Total length: 63km.					design & permitting	long term	Progresses as planned		21
22	22. 57	under consideration (FR)	under consideration (CH)	Reinforcement of the interconnection in the area of Geneva's lake.	< 1000 from FR to CH and < 1500 from CH to FR	3	2					1	under consideration	long term	Progresses as planned. Several technical options (route, technologies) have been designed and are being investigated.	The very uncertain environment, regarding commissioning and decommissioning of generation in particular makes the assessment complex.	France-Switzerland interconnection development under consideration.
23	23. 60	under consideration (FR)	under consideration (BE)	to be determined	1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000 / 1800-3000	3	2	Lille, Ruien area					2	under consideration	2018-2020	Project entered a feasibility study phase. Expected date of comissionning is now 2018.		France-Belgium interconnection development: internal French grid reinforcements, that are prerequisite to maintain the present NTC and further interconnection development under consideration. This project enhance security of supply in Belgium and allows intra and inter countries RES integration.
23	23. A21	Avelin (FR)	Mastaing (FR)	Operation at 400 kV of existing line currently operated at 220 kV					design & permitting	2017	New investment in the TYNDP	Upgrade of all grid assets in Northern France at the same standard	23
23	23. A22	Avelin (FR)	Gavrelle (FR)	Substitution of a new double-circuit 400kV OHL to an existing 400-kV single circuit OHL					design & permitting	2020	New investment in the TYNDP		23
24	24. 60a	Lillo (BE)	Mercator (BE)	Brabo Project : Doubling of the axis Zandvliet-Mercator via Lillo. First part : erecting a new 22km double circuit 380kV OHL with 1500 MVA capacity Lillo and Mercator.	1500	2	2	Antwerp area					2	design & permitting	2017	New date of operation advanced to 2017 due to new generation projects.	Brabo Project	The project aims at ensuring the reliable grid operation to cope with new generation developement in the nothern part of Belgium and more volatile north south flows. It also enhances the security of supply in Antwerp harbour.
24	24. 445	Zandvliet (BE)	Lillo (BE)	Brabo Project : Doubling of the axis Zandvliet-Mercator via Lillo. Second part : erecting a new 22km double circuit 380kV OHL with 1500 MVA capacity Lillo and Zandvliet and a new 400 kV substation in Lillo.					design & permitting	2017	Permits cancelled by national authority . New permitting procedure has started	Brabo Project	24
24	24. 445a	Gramme (BE)	Van Eyck (BE)	Doubling of 108km 380kV axis Gramme-Van Eyck + high performance conductors + new 380 kV substation (Van Eyck)					design & permitting	2014	Permitting phase has started		24
24	24. A26	Horta (BE)	Doel/Mercator (BE)	Upgrade with high performance conductors.					design & permitting	2016-2020	New investment in the TYNDP (The grid simulations performed by Regional Group North Sea showed higher North-South physical flows on nothern Belgian boundary. This project avoid a NTC reduction due to higher loop flows.)		24
24	24. A27	Zandvliet (BE)	0	New PST in Zandvliet substation					planned	2016-2020	New investment in the TYNDP (The grid simulations performed by Regional Group North Sea showed higher North-South physical flows on nothern Belgian boundary. This project avoid a NTC reduction due to higher loop flows)	4th PST on the Belgian north border.	24
25	25. 62	Under Consideration (FR)	Under Consideration (GB)	New subsea HVDC Link between the UK and France. Capacity is still to be determined. (Possibly 1000MW)	1000	1	5					2	under consideration	2019	Further investigations during the feasibility phase have led to reassess the expected commissioning date for "IFA2"		France-UK interconnection development under consideration
26	26. 63	Lienz (AT)	Veneto region (IT)	The project foresees the reconstruction of the existing 220kV-interconnection line as 380kV-line on an optimized route to minimize the environmental impact. Total length should be in the range of 100-150km.	750	3	2					3	planned	long term	Progresses as planned		Reinforcement of the interconnection between Italy and Austria. Also the support the interraction between the RES in mainly Italy with the pump storage in the Austrian Alps.
26	26. 220	Lienz (AT)	0	Erection of a new 220/220kV- PST in the substation Lienz (AT).					under construction	2012	Project is in errecion and expected to be commissioned 2012 according to the schedule	The investment contributes also to project 47.	26
26	26. 47. 216	0	0	0					0	0	0	The investment contributes both to project 26 and project 47. For the technical description see project 47.	26
26	26. 64	Bressanone (IT)	New substation near Innsbruck (AT)	New double circuit 400kV interconnection through the pilot tunnel of the planned Brenner Base Tunnel. Total line length: 65km.					under consideration	>2022	Progresses as planned		26
26	26. 66	Prati di Vizze (IT)	Steinach (AT)	Upgrade of the existing 44km Prati di Vizze (IT) – Steinach (AT) single circuit 110/132kV OHL, currently operated at medium voltage and installing a 110kV/132kV PST.					design & permitting	mid term	Investment delayed with 2 years due to the permitting process		26
26	26. 83	Volpago (IT)	North Venezia (IT)	Realization of a new 380kV line between the existing substation of North Venezia and the future 380kV substation of Volpago, connected in and out to the 380kV "Sandrigo - Cordignano” . Total line length: 31km.					design & permitting	2015	Delays due to authorization process.		26
26	26. 93	Dolo (IT)	Camin (IT)	New 15km double circuit 400kV OHL between existing Dolo and Camin 400kV substations, to be built in parallel with the existing line.					under construction	2014	Authorization process ended, construction phase on going		26
26	26. 97	Polpet (IT)	0	Voltage upgrade of the existing Polpet 150kV/medium voltage substation up to 220kV, complying with 400kV standards. The substation will be connected by two shorts links to the existing Soverzene-Lienz 220kV line.					design & permitting	2015	Authorization process started, project phase on going		26
26	26. 218	Obersielach (AT)	Lienz (AT)	New 190km 380kV OHL connecting the substations Lienz (AT) and Obersielach (AT) to close the Austrian 380kV-Ring in the southern grid area. Line length: 190km.					under consideration	long term	Progresses as planned	The investment contributes also to project 47.	26
26	26. A102	New interconnection between Italy and Austria	0	New possible interconnection line between Italy and Austria					under consideration	long term	This investment replaces investment n°65 mentioned on TYNDP 2010. The previous investment evolved so much that it is substitued by a new project. Feasibility studies ongoing including internal reinforcements.		26
27	27. 68	Okroglo (SI)	Udine (IT)	New 120km double circuit 400kV OHL with installation of a PST in Okroglo. The thermal rating will be 1870 MVA per circuit.	>1800	1	3					2	planned	long term	Progresses as planned		This project increases the capacity between Slovenia - Italy and Slovenia - Hungary. Project will remove congestion and strenghten connection on North-South and East-West axis.
27	27. 92	West Udine (IT)	Redipuglia (IT)	New 40km double circuit 400kV OHL between the existing substations of West Udine and Redipuglia, providing in and out connection to the future 400kV substation of South Udine.					design & permitting	2015	The investment is delayed due to longer than expected authorization procedures.		27
27	27. A96	New interconnection between Italy and Slovenia	0	New interconnection between Italy and Slovenia					under consideration	long term	Feasibility studies ongoing including the internal reinfocements.	Need for strengthening the connection between Slovenia and Italy and increasing of power exchange capability	27
27	27. 223	Cirkovce (SI)	Heviz (HU) Zerjavenec (HR)	The existing substation of Cirkovce (SI) will be connected to one circuit of the existing Heviz (HU) -Zerjavinec (HR) double circuit 400kV OHL by erecting a new 80km double circuit 400kV OHL in Slovenia. The project will result in two new cross-border circuits: Heviz (HU) - Cirkovce (SI) and Cirkovce (SI) - Žerjavenec (HR).					design & permitting	2016	Presently in the authorization process. This investment was delayed due to permitting process.		27
27	27. 224	Krsko (SI)	Bericevo (SI)	New 400kV double circuit OHL. This project will strengthen connection between East and Central part of Slovenia and connect an internal loop. Line length: 80km.					under construction	2015	Authorization process ended, construction phase is on going. This investment was delayed due to permitting process.		27
27	27. 225	Divaca (SI)	Cirkovce (SI)	Upgrading 220kV lines to 400kV in corridor Divaca-Klece-Bericevo-Podlog-Cirkovce. Line length: 193km.					planned	long term	Progresses as planned		27
27	27. A105	Lika(HR)	Brinje(HR)	New 55km single circuit 400 kV OHL replacing aging 220 kV overhead line					planned	2020	Strengthening of the 400 kV corridor across the Adriatic coast in Croatia in LT period and removal of regional congestion at north-south axis , also to accommodate power transfers from Croatia and Bosnia&Herzegovina to Italy through new IT-ME DC link (Investment 70).		27
27	27. A106	Lika(HR)	Velebit(HR)	New 60km single circuit 400 kV OHL replacing aging 220 kV overhead line					planned	2020	Strengthening of the 400 kV corridor across the Adriatic coast in Croatia in LT period and removal of regional congestion at north-south axis , also to accommodate power transfers from Croatia and Bosnia&Herzegovina to Italy through new IT-ME DC link (Investment 70).		27
27	27. A107	Lika (HR)	0	New 400/110 kV substation, 2x300 MVA					planned	2017	Strengthening of the 400 kV corridor across the Adriatic coast in Croatia in LT period and removal of regional congestion at north-south axis , also to accommodate power transfers from Croatia and Bosnia&Herzegovina to Italy through new IT-ME DC link (Investment 70).		27
27	27. A108	Brinje (HR)	0	New 400/220 kV substation, 1x400 MVA					planned	2020	Strengthening of the 400 kV corridor across the Adriatic coast in Croatia in LT period and removal of regional congestion at north-south axis , also to accommodate power transfers from Croatia and Bosnia&Herzegovina to Italy through new IT-ME DC link (Investment 70).		27
27	27. 229	Plomin (HR)	Melina(HR)	New 90 km double circuit OHL, with two connecting substations and transformer 400/220 kV, 400 MVA					design & permitting	>2016	Project moved to long term, due to postponed commissioning date of thermal power plant Plomin		27
27	27. 227	Banja Luka (BA)	Lika (HR)	New 400kV interconnection line between BA and HR					under consideration	2020	End points of OHL and commissioning date defined after bilateral HR-BA agreement		27
28	28. 70	Villanova (IT)	Lastva (ME)	New 1000MW HVDC interconnection line between Italy and Montenegro via 375km 500kV DC subsea cable and converter stations at both ending points.	1000	1	2					3	under construction	2015	Authorization process ended, construction phase on going. The substations on the ME side has been changed.		It contributes significantly to the increase of GTC between the West Balkans and IT such contributing to market integration; complements the ME - IT cable
28	28. 86	Foggia (IT)	Villanova (IT)	New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. A PST will be installed on the new 400kV line.					design & permitting	2015	Progresses as planned		28
28	28. 89	Fano (IT)	Teramo (IT)	New 200km single circuit 400kV OHL between the existing 400kV substations of Fano and Teramo, providing the connection in and out to the future substation to be built in Macerata area.					design & permitting	long term	The investment is delayed due to longer than expected authorization procedures.		28
28	28. 232	Visegrad (BA)	Pljevlja (ME)	New 70km single circuit 400kV OHL between Visegrad and Pljevlja					planned	2015	Feasibility study for 400kV interconnections RS-ME-BA proposed under Infrastructure Projects Facility for Western Balkans		28
28	28. 233a	Lastva (ME)	0	A new substation will be connected to the existing line 400kV Podgorica 2(ME)-Trebinje(BA), with two transformers 2X300MVA 400/110kV, and convertor station for the DC cable Lastva(Tivat)-Villanova (see 70).					design & permitting	2015	Feasibility study covering the aspects of route planning, substation location, environmental and social issues and equipment selection is due to end in second half of 2011		28
28	28. 233b	Lastva (ME)	Pljevlja (ME)	New 160 km double circuit 400kV OHL existing substation Pljevlja and new substation Tivat.					design & permitting	2016	Feasibility study covering the aspects of route planning, substation location, environmental and social issues and equipment selection is due to end in second half of 2011		28
28	28. A109	Bajina Basta (RS)	Visegrad (BA)	New 400kV interconnection OHL between Serbia and BiH, and reconstruction of existing two OHL 220 kV between BiH and Serbia.					planned	>2016	New investment in TYNDP	New 400 kV overhead line between Serbia and BIH. It will eliminate constraints in the region for electric energy transits and exchange.	28
28	28. A110	Bajina Basta (RS)	TPP Obrenovac (RS)	New double circuit 400 kV OHL between new substation Bajina Basta (see infra), and substation Obrenovac					design & permitting	>2016	New investment in TYNDP	Obrenovac is the "strongest" 400 kV node in Serbia, thus providing significant upgrade for evacuation and energy transfer from north to south, and further down in Montenegro, through the new line between Bajina Basta and Pljevlja (ME)	28
28	28. A111	Bajina Basta (RS)	Pljevlja (ME)	New 86 km single circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS).					planned	>2016	New investment in TYNDP		28
28	28. A112	Bajina Basta (RS)	0	New 400/110 kV substation in Bajina Basta, upgrading an existing 220/110 kV substation.					planned	>2016	New investment in TYNDP		28
28	28. A113	Bistrica (RS)	0	New 220/110 kV substation					design & permitting	2015	New investment in TYNDP	After a topology change in the area, the investment will eliminate firm connection in "Vardiste" (secure and stable operation in Serbian network and systems of Bosnia and Herzegovina and Montenegro), to eliminate constraints in the region for electric energy transits and exchange.	28
28	28. A114	Konjsko(HR)	Velebit(HR)	New 100km single circuit 400 kV OHL replacing ageing 220 kV overhead line					planned	2020	Strengthening of the 400 kV corridor across the Adriatic coast in Croatia in LT period and removal of regional congestion at north-south axis , also to accommodate power transfers from Croatia and Bosnia&Herzegovina to Italy through new IT-ME DC link (Investment 70).		28
28	28. 231	Konjsko(HR)	0	Installation of a 150MVAr reactive power device					design & permitting	2014	Investment postponed 1 year due to permitting process		28
28	28. A115	Plat (HR)	0	New 220/110 kV substation					under construction	2013	New investment in TYNDP, contributing to mesh the network surrounding HVDC link IT-ME and to increase the reliability of the EHV system		28
28	28. 228	Trebinhe(BA)	Plat(HR)	Re-establishment of two previously existing 220kV single circuit interconnection Trebinje(BA)-Plat(HR); Total length 10km.					planned	2014	Progresses as planned		28
29	29. 73	El Aouaria (TU)	Partanna (IT)	New 350km 1000 MW HVDC line between Tunisia and Italy via Sicily with 400kV DC subsea cable and converters stations at both ends.	1500	3	5					2	design & permitting	long term	The investment is delayed due to longer than expected authorization procedures.	This project will be realized in 2 steps. In the previous TYNDP just the first part of the investment was mentioned (500MW).	Interconnection between Italy and North Africa.
29	29. 76	Partanna (IT)	Ciminna (IT)	New 65km single circuit 400kV OHL in Sicily between existing Partanna and Ciminna substations.					planned	long term	Progresses as planned		29
29	29. A97	unknown (IT)	unknown (AL)	New interconnection between Italy and Algeria -new DC submarine cable					under consideration	long term	New investment in TYNDP	Need for a new interconnection between Algeria and Italy and increasing of power exchange capability with North Africa frontier. feasibility study on going	29
30	30. 74	Chiaramonte Gulfi (IT)	Sorgente (IT)	Realization of 380kV ring grid, trough the construction of 3 new 380kV line: "Chiaramonte Gulfi - Ciminna", "Sorgente - Ciminna" and "Paternò - Priolo". It will be realized a new 380/150kV substation in Caltanissetta area and the voltage upgrade of the existing Ciminna substation up to 380kV. Total line length: 365km. New 380/150 kV substation in Sorgente area will be temporaly connected in and out to the existing 400 line kV "Paterno - Sorgente" and to the local 220 kV and 150 kV network.	1000	4	1	Palermo, Catania, Agrigento and Messina area					3	planned	2016/long term	Feasibility studies carried out have led to adapt the schedule.		Sicilian 400kV transmission ring.
30	30. 75	Sorgente (IT)	Rizziconi (IT)	New 90km double circuit 400kV line, partly via subsea cable and partly via OHL. This line is part of a larger project that foresees the creation of the future 400kV ring grid of Sicily.					under construction	2014	Delays on construction phase		30
30	30. 77	Partinico (IT)	Fulgatore (IT)	New 45km single circuit 400kV OHL between Partinico and Fulgatore in Western Sicily.					planned	2016	Feasibility studies carried out have led to adapt the schedule.		30
30	30. 87	Feroleto (IT)	Maida (IT)	New 400kV OHL across Calabria between the existing substation of Feroleto and the future substation of Maida, while restructuring the existing grid in North Calabria.					design & permitting	mid term	Delays due to authorization process.		30
30	30. A98	Mineo (IT)	0	New 380/150 kV substation in Mineo area connected in and out to the existing 400 line kV "Chiaramonte Gulfi - Paterno" and to the local HV network.					planned	long term	New investment in TYNDP	needed to overcome the expected congestions on the central-east HV network of Sicily affected by the flows of consistent production from renewable plants	30
31	31. 85	Pavia area (IT)	Piacenza area (IT)	New 45km double circuit 400kV OHL between 2 substations in the Pavia area and Piacenza.	>1000	3					2	planned	long term	Initial design partially changed, with new reinforcements and rearrangements activities on the neighbouring areaas resulting from further studies		Increase interconnection capability between IT and CH.
31	31. 95	Mese (IT)	0	Voltage upgrade of the existing 220/132kV Mese substation up to 400kV.					design & permitting	2014	Delays due to authorization process.		31
31	31. 99	Avise (IT)	Chatillon (IT)	Voltage upgrade of the existing 40km Avise-Villeneuve-Chatillon single circuit 220kV OHL up to 400kV.					design & permitting	2014	Delays due to authorization process.		31
31	31. 100	Milan (IT)	0	Restructuring of the 220kV network in the urban area of Milan. Some new 220kV cables (33km), a new 220kV substation (Musocco) and some reinforcements of existing assets (35km) are planned.					design & permitting	mid term	The cables in the mIlan area are in operation, the appropriate substations are under construction and the reinforcements are under design and permitting.		31
31	31. 103	Brescia (IT)	0	New 400/132kV substation in South East area of Brescia, connected in and out to the existing Flero-Nave 400kVOHL, while restructuring the 132kV network.					planned	mid term	Progresses as planned		31
31	31. 112	Tirano (IT)	Verderio(IT)	New 140km single circuit 400kV OHL between Tirano and Verderio substations connecting also the new 400kV substation Grosio/Piateda.					planned	long term	Progresses as planned		31
31	31. 124	Mettlen (CH)	Airolo (CH)	Upgrade of existing 225kV OHL into 400kV. Line length: 90km.					under consideration	2020	Progresses as planned		31
31	31. A101	New interconnections between Italy and Switzerland	0	Up to 4 interconnection projects are under discussion, one or two probably will be implemented					under consideration	long term	This investment replaces investment n° 120 mentioned on TYNDP 2010. The previous investment evolved so much that it is substitued by a new project. Feasibility studies ongoing including the internal reinforcements.		31
32	32. 88	Montecorvino (IT)	Benevento (IT)	New 70km double circuit 400kV OHL between the existing 400kV substations of Montecorvino and Benevento II, providing in and out connection to the future substation to be build in Avellino North area, which will be also connected to the existing "Matera-S. Sofia" 400kV line.	1900	4	1	Naple urban area, Sorrento Penninsul, minor Campania islands and Tirrenic South coast Italy					3	design & permitting	mid term	The Avelino substation is under construction, the line is in delay due to authorization process.		Reinforcement between South and Central-South of Italy to accommodate increasing market flows.
32	32. 91	Foggia (IT)	Benevento II (IT)	Upgrade of the existing 85km Foggia-Benevento II 400kV OHL and installation of a PST on this line.					under construction	2013-2014	Authorization process ended, construction phase on going		32
32	32. 96	Deliceto (IT)	Bisaccia (IT)	New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area.					design & permitting	mid term	The 2 substations are in operation from 2011. The connecting line is still in design and permitting.This delay is due to authorization process.		32
32	32. 96a	Several new 380 kV substations in Central / South of Italy for RES (IT)	0	It will be realized few new 380/150kV substations. The new substations will be connected to the wind power plants in order to avoid the congestions on the 150kV network and to dispatch the renwable energy produced.					under construction	mid term	The realisation of the substations is delayed. These investments are higly sensitive to the construction fo the wind/solar plants that are meant to connect.		32
32	32. 102	Naples (IT)	0	Restructuring of the 220kV network in the urban area of Naples. Some new 220kV cables and some reinforcements of existing assets are planned. Total length: 36km.					design & permitting	long term	Progresses as planned		32
32	32. 110a	Aliano (IT)	Montecorvino (IT)	New connection OHL 400 kV between north Basilicata and Campania region.					planned	long term	Progresses as planned		32
32	32. A99	Restructuring of North Calabria (IT)	0	New 400kV OHL between the existing substations of Laino and Altomonte in Calabria and a new 380/150 kV substation in Aliano connected in and out to the existing 400 line kV "Matera - Laino" and to the local HV network. Related to this project will be acted a great restructuring of the local HV network, downgrading the existing 220 kV lines to 150 kV level and the demolition of great part of existing 150 kV lines inside the Pollino Park.					partly under construction, design & permitting	2012/mid term	New investment in TYNDP (initial design partially changed, evolution including new reinforcements and rearrangements activities on the neighbouring areas resulting from further studies)		32
33	33. 90	Calenzano (IT)	Colunga (IT)	Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards).	500	2	5	central part of Italy					2	design & permitting	mid term	Delays due to authorization process.		Reinforcement between Northern and Central part of Italy to accommodate increasing market flows.
33	33. 94	Mantova area (IT)	Modena area (IT)	New 35km 400kV OHL between the 2 substations in Modena and Mantova area.					planned	long term	During the preliminary consultation process the substations have became uncertain.		33
33	33. 104	Rome (IT)	0	Restructuring of the network in the Rome area. The work consists of : a new 380/150kV substation in south-West area of Rome, connected in and out to the existing 380kV line "Rome West-Rome South", a voltage upgrade of the existing Flaminia substation up to 380kV to be connected in and out to the foreseen 380kV line "Rome West - Rome North" and a restructuring of the 150kV network.					design & permitting	2013/long term	Progresses as planned		33
33	33. 109	North Bologna (IT)	0	New 400/132kV substation in North Bologna area connected in and out to the existing Sermide–Martignone 400kV line.					design & permitting	mid term	Delays due to authorization process.		33
33	33. 111	Lucca (IT)	0	New 380/132kV substation in Lucca area connected in and out to the existing 380kV line “La Spezia-Acciaiolo”.					planned	long term	Progresses as planned		33
33	33. 113	Monte S. Savino (IT)	0	New 400/220/132kV substation in Monte S. Savino area connected to the existing S. Barbara 400kV substation by upgrading an existing 220kV line.					design & permitting	2015/long term	Delays due to authorization process.		33
34	34. A100	Codrongianos (IT)	Suvereto (IT)	Repowering of existing HVDC interconnection between Sardinia, Corse and mainland Italy via 220kV DC subsea cable (358km). The first connection is in operation since 1970. Total capacity of the bipolar link: 500MW.	500	4	1					2	planned	long term	New investment in TYNDP.		Reinforcement between Sardinia Corso and mainland Italy.
35	35. 137	Vitkov (CZ)	Mechlenreuth (DE)	New 400kV single circuit tie-line between new (CZ) substation and existing (DE) substation. Length: 70km.	500	5	4					3	under consideration	long term	Progresses as planned		This project is requered to enable power flows between West and East, enhance the transfer capability between CZ and DE and supports the future generation evacuation.
35	35. 138	tbd (CZ)	tbd (DE) - South-Eastern part of 50Hertz Transmission control area (Röhrsdorf)	Possible increase of interconnection capacity between CEPS and 50Hertz Transmission is under consideration: either a new 400kV tie-line (OHL on new route) or a reinforcement of the existing 400kV tie-line Hradec (CEPS) – Röhrsdorf (50Hertz Transmission).					under consideration	long term	Progresses as planned		35
35	35. 306	Vitkov (CZ)	0	New 400/110kV substation equipped with transformers 2x350MVA.					planned	2017/2018	It is closely dependent on construction of line investment n°308		35
35	35. 307	Vernerov (CZ)	0	New 400/110kV substation equipped with transformers 2x350MVA.					planned	2013/2016	Commissionning date has been divided into two phases (1. phase - temporary connection of wind plant 180MW, 2. phase finalization of substation constraction including connection to the distribution grid (consumption)		35
35	35. 308	Vernerov (CZ)	Vitkov (CZ)	New 400kV double circuit OHL, 1385 MVA.					planned	long term	Permitting procedure complications are foreseen (line crosses protected area)		35
35	35. 309	Vitkov (CZ)	Prestice (CZ)	New 400kV double circuit OHL, 1385 MVA.					under consideration	long term	Permitting procedure complications are foreseen (line cosses protected area)		35
35	35. 311	Kocin (CZ)	0	Upgrade of the existing substation 400/110kV; upgrade transformers 2x350MVA.					design & permitting	long term	Schedule harmonization with market participants		35
35	35. 312	Mirovka (CZ)	0	Upgrade of the existing substation 400/110kV with two transformers 2x250MVA.					planned	long term	Schedule harmonization decided with market participants		35
35	35. 313	Kocin (CZ)	Mirovka (CZ)	Connection of 2 existing 400kV substations with double circuit OHL having 120.5km length: and a capacity of 2X1385 MVA.					planned	long term	Schedule harmonization decided with market participants		35
35	35. 314	Mirovka (CZ)	V413 (CZ)	New double circuit OHL with a capacity of 2x1385 MVA and 26.5km length.					planned	long term	Schedule harmonization decided with market participants		35
35	35. 315	Kocin (CZ)	Prestice (CZ)	Adding second circuit to existing single circuit line OHL upgrade in length of 115.8km. Target capacity 2x1385 MVA.					planned	long term	Schedule harmonization decided with market participants		35
35	35. 316	Mirovka (CZ)	Cebin (CZ)	Adding second circuit to existing single circuit line (88.5km, 2x1385 MVA).					under consideration	long term	Schedule harmonization decided with market participants		35
35	35. 317	Hradec (CZ)	Reporyje (CZ)	Upgrade of existing 400kV single circuit OHL with length of 116.9km. Target capacity 1385 MVA.					completed	commissioned	Commissioned		35
36	36. 141	Ishøj/Bjæverskov (DK)	Bentwisch/Güstrow (DE)	The Kriegers Flak Combined Grid Solution is the new offshore multiterminal connection between Denmark and Germany used for both grid connection of offshore wind farms Kriegers Flak and interconnection. Technical features still have to be determined.	600	5	3					1	planned	long term	Permission for Danish Wind Farm KF 3 is in pending. Connection to Sweden is withdrawn at present, but can come on a later stage.		The Kriegers Flak Combined Grid Solution is the new offshore multiterminal connection between Denmark and Germany used for both grid connection of offshore wind farms Kriegers Flak and interconnection.
37	37. 142	Tonstad (NO)	tbd (DE)	Nord.Link/NorGer: a new HVDC connection between Southern Norway and Northern Germany. Estimated subsea cable length: 520 - 600km. Capacity: 1000 MW.	1000-1400	1	4					3	design & permitting	2018/2021	Revised capacity and progress postponed, due to more demanding system operations and time needed to obtain necessary government permits for reinforcing the national grid.		The purpose is: Market integration with the continent and facilitating RES integration in southern and western Norway. Will also improve security of supply in southern Norway.
	37. 408	Kristiansand, Feda (NO)	0	Reactive compensation due to HVDC links NorNed and Skagerak 4. Reactive power devices in 400kV substations.					design & permitting	2012/2014	Feda is in the planning and permitting stage. Kristiansand is under construction(commissioned expected as planned 2012)
37	37. 406	(Southern part of Norway) (NO)	0	Voltage uprating of existing 300 kV line Sauda/Saurdal - Lyse - Tonstad - Feda - 1&2, Feda - Kristiansand; Sauda-Samnanger in long term.Voltage upgrading of existing single circuit 400kV OHL Tonstad-Solhom-Arendal. Reactive power devices in 400kV substations.					design & permitting	2016 (2013-2018)	Revised progress. Due to more demanding system operations and time needed to obtain necessary government permits for reinforcing the national grid. The investment now embed former TYNDP 2010's investments 407 and 409 and the technical description has been updated accordingly.		37
38	38. 425	Feda (NO)	tbd (NL)	NorNed 2: a second HVDC connection between Norway and The Netherlands via 570km 450kV DC subsea cable with 700 - 1400MW capacity.	700	5	2					2	under consideration	Long term	NorNed 2 is now not likely be realised during this planning period but is included in the TYNDP calculations and therefore on the project list. NorNed 2 is not included in the current Norwegian national grid development plan.		Additional interconnection between NO and NL under consideration
39	39. 428	Kassø (DK)	Tjele (DK)	Rebuilding of a 400kV OHL of 173km from a single-circuit to a double-circuit . This increases the transfer capacity with approx 1000 MW.	1000-1550	1	2					2	design & permitting	2012/2014	Progresses as planned		Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity.
39	39. 144	Audorf (DE)	Kassö (DK)	Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity. It consists of partially an upgrade of existing 400kV line and partially a new 400kV route in Denmark. In Germany new 400kV line mainly in the trace of a existing 220kV line. The total length of this OHL is 114km.					under consideration	2017	Progresses as planned		39
40	40. 446	Bascharage (LU)	Aubange (BE)	As a first step(2016) a PST could be placed in the existing 225kV line between LU and BE. In a second stage, two solutions are currently investigated (4 TSOs - Elia, Amprion, CREOS, RTE are involved). Solutions 1 would be a new interconnection between Creos grid in LU and ELIA grid in BE via a 16km double circuit 225kV underground cable with a capacity of 1000 MVA. Solution 2 would be the interconnextion between CREOS grid in LU and ELIA grid in BE via a new 380 kV double circuit. The current study will investigate the impact of this new interconnection on other boundaries (impact of loop flow) and on internal grids . The potential reinforcements of the other boundaries and the internal grids will also be taken into account in the evaluation.	380-900	2	5	Luxemburg area					2	under consideration	2016/2020	The comissionning date and status changed as the study to determine the best investment is still ongoing.		Increase the transfer capability between LU,DE, BE and FR.
40	40. A29	Bascharage (LU)	tbd (BE, DE, &/o FR)	New interconnection with neighbour(s) either 220kV or 400kV					under consideration	2020	New investment in TYNDP	An ongoing network study (4 TSOs involved) investigates the robustness of the planned 220kV connection between LU and BE and the potentially need for an upgrading to a 400kV interconnector in the South.	40
40	40. 447	Heisdorf (LU)	Berchem (LU)	New 20km double-circuit mixed (underground cable+OHL) 225kV project with 1000 MVA capacity including substations for infeed in lower voltage levels.					design & permitting	2012/2017	Progresses as planned		40
40	40. A30	Bascharage (LU)	Niederstedem (DE) or tbd (DE)	Upgrading and new construction of an interconnector to DE, in conjunction with the interconnectorin the south of LU; Partial upgrading of existing 220kV lines and partial new construction of lines; With power transformer station in LU					under consideration	2020	New investment in TYNDP		40
41	41. 149	Dollern (DE)	Stade (DE)	New 400kV double circuit OHL Dollern - Stade including new 400kV switchgear in Stade. Length:14km.	>3000	4	5					1	design & permitting	mid term	This investment depends on the commissioning of a conventional power plant in the area. The additional reason for delay is the long permitting procedure associated with this investment.		Evacuation of the new conventional generation in the 50Hz and TenneT area.
41	41. 150	Conneforde (DE)	Maade (DE)	New 400kV double circuit ( underground cable+OHL) Conneforde - Maade including new 400kV switchgear Maade. Length: 37km.					design & permitting	long term	Progresses as planned		41
41	41. A74	North of Control Area 50HzT (DE)	0	Construction of new substations/lines for integration of newly build power plants in northern part of 50HzT control area.					planned	long term	New investment in TYNDP, because of additionnal need for generation evacuation. Some of the investments are to be commissioned by the mid term and the some by long term.	Support of conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.	41
42	42. 152	Dörpen/West (DE)	0	New substation for connection of offshore wind farms.	>8000	4	1					3	under construction	mid term	Progresses as planned	Commercially sensitive information about this new wind-farm connection cannot be displayed in the TYNDP report	Integration of the offshore wind parks and the onshore grid reinforcemetns in the Northern DE.
42	42. 159	Cluster BorWin1 (DE)	Diele (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 205km. Line capacity: 400MW.					under construction	mid term	The commission date of this wind farms connection should be in 2012. Energy transportation is however already enable	Due to nondisclosure aggreements it is not possible to give further information about this wind farm connection in TYNDP	42
42	42. 160	Offshore- Wind park Nordergründe (DE)	Inhausen (DE)	New AC-cable connection with a total length of 35km.					design & permitting	mid term	Progresses depend on development of the off shore wind farm		42
42	42. 161	Offshore- Wind park GEOFreE (DE)	Göhl (DE)	New AC-cable connection with a total length of 32km.					design & permitting	mid term	Progresses depend on development of the off shore wind farm		42
42	42. 163	Cluster HelWin1 (DE)	Büttel (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 145km. Line capacity: aprox. 690MW. This Project includes also a new substation Büttel and connection of this new substation with the existing OHL Brünsbüttel - Wilster.					under construction	mid term	Progresses with delay.	Due to nondisclosure aggreements it is not possible to give further information about this wind farm connection in TYNDP	42
42	42. 164	Cluster SylWin1 (DE)	Büttel (DE)	New line consisting of underground +subsea cable with a total length of 210km. Line capacity: aprox.864MW.					under construction	mid term	Progresses as planned	Due to nondisclosure aggreements it is not possible to give further information about this wind farm connection in TYNDP	42
42	42. 165	Cluster DolWin1 (DE)	Dörpen/West (DE)	New line consisting of underground +subsea cable with a total length of 155km. Line capacity: 800MW.					under construction	mid term	Progresses as planned	Due to nondisclosure aggreements it is not possible to give further information about this wind farm connection in TYNDP	42
42	42. 166	Offshore Wind park Riffgat (DE)	Emden /Borßum(DE)	New AC-cable connection with a total length of 80km.					under construction	mid term	Progresses as planned	Due to nondisclosure aggreements it is not possible to give further information about this wind farm connection in TYNDP	42
42	42. 167	Cluster BorWin2 (DE)	Diele (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 205km. Line capacity: 800MW.					under construction	mid term	Progresses as planned	Due to nondisclosure aggreements it is not possible to give further information about this wind farm connection in TYNDP	42
42	42. A82	Cluster DolWin2 (DE)	Dörpen/West (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 160 km. Line capacity: 900 MW					under construction	mid term	New investment in TYNDP, for connection of new off-shore wind-farms	Due to nondisclosure aggreements it is not possible to give further information about this wind farm connection in TYNDP	42
42	42. A83	Cluster DolWin3 (DE)	Dörpen/West (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 160 km. Line capacity: 900 MW					design & permitting	mid term	New investment in TYNDP, for connection of new off-shore wind-farms		42
42	42. A84	Cluster BorWin3	Dörpen/West (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 180 km. Line capacity: 900 MW					design & permitting	mid term	New investment in TYNDP, for connection of new off-shore wind-farms		42
42	42. A85	Cluster HelWin2	Büttel (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 145km. Line capacity: 690 MW					under construction	mid term	New investment in TYNDP, for connection of new off-shore wind-farms	Due to nondisclosure aggreements it is not possible to give further information about this wind farm connection in TYNDP	42
42	42. A86	Cluster BorWin4 (DE)	Emden/Ost (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 185 km. Line capacity: 900 MW					under consideration	long term	New investment in TYNDP, for connection of new off-shore wind-farms		42
42	42. A87	Cluster SylWin2 (DE)	Büttel (DE)	New HVDC transmission systm consisting of offshore plattform, cable and converters with a total length of 210km. Line capacity: 800 MW					under consideration	long term	New investment in TYNDP, for connection of new off-shore wind-farms		42
42	42. 211	Further connections of more offshore wind farms (DE)	0	Further connections in the clusters BorWin, DolWin, SylWin and HelWin.					under consideration	long term	Progresses depend on development of the off shore wind farm		42
43	43. A81	Rhine Ruher area (DE)	Area of Stuttgart (DE)	New DC-lines to integrate new wind generation especially from North/ Baltis Sea towards Central-South Europe for consumption and storage.	9000	1	2	Bavaria and Baden-Wurtenbergh area					3	under consideration	long term	New investment in TYNDP, due to long distance RES integration; voltage stability of the grid; SOS in the South of Germany		Combined DC and AC new infrastructure to accommodate the new RES generation, the associated flows from North to South and also secure the SOS in South Germany.
43	43. A88	Area of Schleswig-Holstein (DE)	Grafenrheinfeld (DE), Isar (DE) and Oberbachern (DE)	New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage					under consideration	long term	New investment in TYNDP, due to long distance RES integration; voltage stability of the grid; SOS in the South of Germany		43
43	43. A75	Area of Mannheim (DE)	Area of Magdeburg (DE)	NewDC- lines to integrate new wind generation from Baltic Sea towards Central/south Europe for consumption and storage					under consideration	long term	New investment in TYNDP, due to long distance RES integration; voltage stability of the grid; SOS in the South of Germany		43
43	43. A89	Area of Northern Lower Saxony (DE)	0	New lines for integrattion of on- and offshore Windgeneration					under consideration	long term	New investment in TYNDP, due to new wind generation projects		43
43	43. A90	Area of Schleswig-Holstein (DE)	0	About 300 km new 380-kV-lines and around 24 new transformers for integration of onshore Wind in Schleswig-Holstein					under consideration	long term	New investment in TYNDP, due to new wind generation projects		43
44	44. 147	Dollern (DE)	Hamburg/Nord (DE)	New 400kV double circuit OHL Dollern - Hamburg/Nord including one new 400/230kV transformer in substation Hamburg/Nord and new 400kV switchgear Kummerfeld. Length:43km.	>4000	1	2	Bavaria and Baden-Wurtenbergh area					3	design & permitting	mid term	Delays due to authorization process.		This project helps accomodating the increasing flows coming mainly form RES in NW DE to SW DE and CH.
44	44. 148	Audorf (DE)	Hamburg/Nord (DE)	New 400kV double circuit OHL Audorf - Hamburg/Nord including two new 400/230kV transformers in substation Audorf. Length: 65km.					design & permitting	mid term	This investment was schedulted for 2015. Presently it is foreseen a delay of around 1 year due to permitting process.		44
44	44. 151	Wehrendorf (DE)	Ganderkesee (DE)	New line (length: ca. 95km), extension of existing and erection of substations, erection of 380/110kV-transformers.					design & permitting	mid term	Delays due to authorization process.		44
44	44. 156	Niederrhein (DE)	Dörpen/West (DE)	New 400kV double circuit OHL Dörpen - Niederrhein including extension of existing substations. Length: 167km.					design & permitting	mid term	Delays due to authorization process.		44
44	44. 157	Wahle (DE)	Mecklar (DE)	New 400kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km.					design & permitting	mid term	Delays due to authorization process.		44
44	44. 170	Großgartach (DE)	Hüffenhardt (DE)	New 380kV OHL. Length: 23km. Included with the project : 1 new 380kV substation, 2 transformers.					under construction	2012	Progresses as planned		44
44	44. 171	Hüffenhardt (DE)	Neurott (DE)	Upgrade of the line from 220kV to 380kV. Length: 11km. Included with the project : 1 new 380kV substation.					planned	2020	Progresses as planned		44
44	44. 172	Mühlhausen (DE)	Großgartach (DE)	Upgrading line from 220kV to 380kV. Length:-45km.					design & permitting	2014	Progresses as planned		44
44	44. 173	Hoheneck (DE)	Endersbach (DE)	Upgrading line from 220kV to 380kV. Length:20km.					design & permitting	2014	Progresses as planned		44
44	44. 174	Bruchsal Kändelweg (DE)	Ubstadt (DE)	A new 380kV OHL. Length:6km.					design & permitting	2014	Postponed from one year due to permitting procedures		44
44	44. 176	Villingen (DE)	Weier (DE)	A new 380kV OHL. Length:75km.					under consideration	2020	Progresses as planned		44
44	44. 178	Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)Baden-Württemberg, / Süden & Nordosten (DE)	0	Installation of 2x250 MVAr 380kV capacitance banks.					under construction	2014	One more bank in addition. Two have already been installed. Projects realised earlier because the need for reactive power compensation became urgent.		44
44	44. 179	Rommerskirchen (DE)	Weißenthurm (DE)	New line, extension of existing and erection of substations, erection of 380/110kV-transformers. Total line length: 100km.					under construction/design & permitting	mid term	Some parts are commissioned but the main elements of the investment are still in design and permitting due to delays in permittign process.		44
44	44. 181	Dauersberg (DE)	Limburg (DE)	New 380kV double circuit OHL, extension of existing of substations, Total line length: 20km.					under construction/design & permitting	mid term	Some parts are commissioned but the main elements of the investment are still in design and permitting due to delays in permittign process.		44
44	44. 182	Kriftel (DE)	Eschborn (DE)	On the main distance upgrading line: total lenth: 10 km					under construction/design & permitting	mid term	Some parts are commissioned but the main elements of the investment are still in design and permitting due to delays in permittign process.		44
44	44. A80	Area of West Germany (DE)	0	Installation of sveral 300 MVAr 380kV capacitance banks, extension of existing substations.					under consideration	long term	New investment in TYNDP, because of additional needs for RES integration (combined with SoS)		44
44	44. A79	Cloppenburg (DE)	North Baden-Wuerttemberg (DE)	New lines and installation of additional circuits, extension of existing and erection of several EHV-substations.					under consideration	long term	RES integration combined with pump storage in the alp region (market) / increasing of the NTC		44
44	44. 183	Wehrendorf (DE)	0	Installation of 300 MVAr 380kV capacitance banks, extension of existing substations.					design & permitting	mid term	Delays due to authorization process.		44
44	44. 184	Bürstadt (DE)	0	Installation of 2 x 300 MVAr 380kV capacitance banks, extension of existing substations.					design & permitting	mid term	Delays due to authorization process.		44
44	44. 185	Area of Muensterland and Westfalia (DE)	0	New lines and installation of additional circuits, extension of existing and erection of several 380/110kV-substations. Total length: ca. 110km.					design & permitting	long term	Delays due to authorization process.		44
44	44. 186	Gütersloh (DE)	Bechterdissen (DE)	New lines and installation of additional circuits, extension of existing and erection of 380/110kV-substation. Total line length:27km.					under construction	mid term	Delays due to authorization process.		44
44	44. 187	Area of West-Rhineland (DE)	0	New lines and installation of additional circuits, extension of existing and erection of several 380/110kV-substations.					under construction	2013	Progresses as planned		44
44	44. 188	Kruckel (DE)	Dauersberg (DE)	New lines, extension of existing and erection of several 380/110kV-substations. Total line length: 130km.					planned	long term	Progresses as planned		44
44	44. A78	Weissenthurm (DE)	Niederstedem (DE)	Construction of new 380kV double-circuit OHLs, decommissioning of existing old 220kV double-circuit OHLs, extension of existing and erection of several 380/110kV-substations. Length: 105km.					planned	long term	New investment in TYNDP	RES integration/ Market integration especially east-west-direction	44
44	44. A77	Area of South-Wuerttemberg (DE)	0	Construction of new 380kV double-circuit OHLs, decommissioning of existing double-circuit OHLs, extension of existing 380-kV-substations. Length: ca. 60km.					planned	long term	New investment in TYNDP	RES integration combined with pump storage in the alp region (market) / increasing of the NTC DE-CH/AT	44
44	44. 190	Saar-Pfalz-Region (DE)	0	New lines, extension of existing and erection of several 380/110kV-substations. Upgrade of an existing line from 220 to 380 kV					planned	long term	Delays due to authorization process.	SoS (Neub. Frltg Fraulaut-Saarwellingen) combined with RES integration	44
44	44. 175	Birkenfeld (DE)	Ötisheim (DE)	A new 380kV OHL. Length:11km.					planned	2020	New investment in TYNDP		44
44	44. 189	Niederrhein (DE)	Utfort (DE)	New 380kV double-circuit OHL in South-Eastern part of 50Hertz Transmission control area. Total length: 105km.					under consideration	long term	New investment in TYNDP		44
45	45. 90. 177	0	0		>2000	1	2	Bavaria and Baden-Wurtenbergh area					3			0	The investment contributes both to project 45 and project 90. For the technical description see project 90.	This project helps accomodating the increasing flows coming mainly form RES in NE DE to South DE and to the Alps.
45	45. 191	Neuenhagen (DE)	Vierraden (DE)	Project of new 380kV double-circuit OHL Neuenhagen-Vierraden-Bertikow with 125km length as prerequisite for the planned upgrading of the existing 220kV double-circuit interconnection Krajnik (PL) – Vierraden (DE Hertz Transmission).					design & permitting	2013/2015	Project in permitting phase, strong local resistance		45
45	45. 193	Halle/Saale (DE)	Schweinfurt (DE)	New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been comissioned. / Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is rigt downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids.					design & permitting	mid term	project partly completed, strong local public resistance- delay due to permitting process		45
45	45. 197	Neuenhagen (DE)	Wustermark (DE)	Construction of new 380kV double-circuit OHL between the substations Wustermark-Neuenhagen with 70km length. Support of RES and conventional generation integration, maintaining of security of supply and support of market development.					under construction	mid term	Project partly under construction and partly in permitting phase. Expected date of commissioning was adjusted due to long permitting process and strong local public resistance.		45
45	45. 199	Western Pomerania (DE)	Uckermark North (DE)	Construction of new 380kV double-circuit OHLs in North-Eastern part of 50HzT control area and decommissioning of existing old 220kV double-circuit OHLs. Length: 135km.Support of RES and conventional generation integration in North Germany, maintaining of security of supply and support of market development.					planned	2015	Progresses as planned		45
45	45. 200	Lubmin (DE)	Erfurt area (DE)	380-kV-grid enhancement and structural change area Lubmin-Stralsund and area Magdeburg/Wolmirstedt					planned	long term	Progresses as planned		45
45	45. 202	Area upper Lausitz(DE)	Area Gera(DE)	Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.Upgrading of several existing double-circuit 380kV OHL in the South-Eastern part of the control area of 50Hertz Transmission. Total length: 190km. / Support of RES and conventional generation integration in North-Eastern Germany, maintaining of security of supply and support of market development.					design & permitting	2017	Progresses as planned		45
45	45. 204	Area south of Magdeburg(DE)	Förderstedt (DE)	Construction of new 380kV double-circuit OHL between substations south of Magdeburg with 80 km length and double connection/loop in for Förderstedt					planned	mid term / long term	Investment delayed due to longer than expected permitting process. The date mentioned in the TYNDP 2010 was a typing mistake.		45
45	45. 205	Fördertsedt	Area Magdeburg(DE)	Construction of new 380kV double-circuit OHL between the substations Förderstedt-Klostermansfeld-Lauchstädt with 80 km length and double connection/loop in for Förderstedt; Reinforcement of existing switchgear, Support of RES and conventional generation integration, maintaining of security of supply and support of market development.					planned	2015/2020	Progresses as planned		45
45	45. 206	Area Leipzig(DE)	Area Chemnitz(DE)	Upgrade of existing double-circuit 380-kV-overhead lines (length: 50km) and also construction of 70km of new 380 kV-double-circuits OHL in Saxony and double-connection/loop in Weida					under consideration	2020	Progresses as planned		45
45	45. 207	Substations in South-Western part of 50Hertz Transmission control area (DE)	0	Construction of new 380kV substation in Southern Magdeburg area and decommissioning of existing old 220kV equipment. Upgrading of the existing double-circuit 380kV OHL. 50 km					planned	long term	Some of the investments are to be commissioned by the mid term and the some by long term.		45
45	45. 208	Lines and Substations in South-Western part of 50Hertz Transmission control area (DE)	0	Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.Construction of new 380kV double-circuit OHL with about 260 km / Upgrading of the existing double-circuit 380kV OHL. Length: 190km. / Support of RES and conventional generation integration, maintaining of security of supply and support of market development.					planned	2015/2020	Progresses as planned		45
45	45. 209	Substations in 50Hertz Transmission control area	0	extension of existing and erection of new 380 kV-substations and several 380/110kV-substations.					design & permitting	mid term	This investment includes several substations in the control area of 50Hertz Transmission control area. Present status varies form design & permitting, planning to under consideration and the date of commissioning varies from short/mid to long term.		45
45	45. 153	Redwitz (DE)	Grafenrheinfeld (DE)	Upgrade of 230kV connection Redwitz - Grafenrheinfeld to 400kV, including new 400kV switchgear Eltmann. Line length: 97km.					design & permitting	mid term	Investmetn delay due to delay in the implementaiton fo the line Halle-Schweinfurt(investment 45. 193)		45
45	45. 154	Redwitz (DE)	0	New 500 MVAr SVC in substation Redwitz.					planned	mid term	Progresses as planned		45
45	45. 155	Raitersaich (DE)	0	New 500 MVAr SVC in substation Raitersaich.					planned	mid term	Progresses as planned		45
45	45. 47. 158	0	0	0					0	0	0	The investment contributes both to project 45 and project 47. For the technical description see project 47.	45
46	46. 194	wind farm cluster Baltic Sea East (DE)	Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)Lüdershagen/ / Lubmin (DE)	Offshore wind farm connection project (by AC-cables on transmission voltage level or by clustering with DC connections) has to be constructed and afterwards also to be operated by the TSO (in this project: 50Hertz Transmission) according to German law.	>2000	4	1					1	design & permitting	2012-2020	This investment includes several connections of offshore wind farms in the eastern part of the Baltic Sea. The present expected date of commissioning varies from 2012 to 2020.		The integration of offshore wind geenration in the Baltic Sea.
46	46. 195	wind farm cluster Baltic Sea West (DE)	Bentwisch (DE)	Offshore wind farm connection project (by AC-cables on transmission voltage level or by clustering with DC connections) has to be constructed and afterwards also to be operated by the TSO (in this project: 50Hertz Transmission) according to German law.					design & permitting	2013-2020	This investment includes several connections of offshore wind farms in the western part of the Baltic Sea. The present expected date of commissioning varies from 2013 to 2020.		46
47	47. A76	Vöhringen / Leupolz (DE)	Westtirol (AT)	Upgrade of an existing OHL to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers	>2000	1	2					3	planned	long term	New investment in TYNDP		The reinforcement of the interconnection between Austria and Germany. Also the support the interraction between the RES in Northern Europe(mainly DE) with the pump storage in the Austrian Alps.
47	47. 158	Irsching (DE)	Ottenhofen (DE)	Upgrade of 230kV connection Irsching - Ottenhofen to 400kV, including new 400kV switchgear Zolling. Length 76km.					planned	mid term	Progresses as planned	The investment contributes also to project 45.	47
47	47. 212	Isar / Ottenhofen (DE)	St. Peter (AT)	New 400kV double circuit OHL Isar - St. Peter including new 400kV switchgears Altheim, Simbach and St. Peter, and one new 400/230kV transformer in substation Altheim and fourth circuit on line Isar - Ottenhofen. Line length: 90km.					design & permitting	2017	Progresses as planned		47
47	47. 216	St. Peter (AT)	Tauern (AT)	Completion of the 380kV-line St. Peter - Tauern. This contains an upgrade of the existing 380kV-line St. Peter - Salzburg from 220kV-operation to 380kV-operation and the erection of a new internal double circuit 380kV-line connecting the substations Salzburg and Tauern (replacement of existing 220kV-lines on optimized routes). Moreover the erection of the new substations Wagenham and Pongau and the integration of the substations Salzburg and Kaprun is planned. Line length: 130km.					design & permitting	2017/2019	Preparation for the permitting procedure is ongoing. APG is making efforts to set the 380-kV-Salzburg-line 2017 into service. Depending on possible delays during the permitting procedure the commissioning is expected between 2017 and 2019	The investment contributes also to project 26.	47
47	47. 26. 218	0	0	0					0	0	0	The investment contributes both to project 26 and project 47. For the technical description see project 47.	47
47	47. 219	Westtirol (AT)	Zell-Ziller (AT)	Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of additional 220/380kV-Transformers. Line length: 105km.					partly under construction	2013-2020	Project consists of several measures and is on shedule		47
47	47. 26. 220	0	0	0					0	0	0	The investment contributes both to project 26 and project 47. For the technical description see project 47.	47
47	47. 221	St. Peter (AT)	Ernsthofen (AT)	Upgrade from 220kV-operation to 380kV and erection of a 380kV-Substation in Ernsthofen and St. Peter.					under construction	2013	The project is on schedule. Permissions are obtained. Commissioning is expected for 2013		47
48	48. 214	Gabcikovo (SK)	Gőnyü area (HU)	New interconnection (new 2x400 kV tie-line) between SK and HU starting from Gabčíkovo substation (SK) to the Gőnyü substation on Hungarian side ( preliminary decision). Project also includes the erection of new switching station Gabčíkovo next to the existing one.	1100 SK -> HU; HU -> SK 400	3	2	(North-West Hungary)					1	under consideration	2016	The commissioning date has been moved to earlier term due to earlier erection of new 400 kV line Veľký Ďur - Gabčíkovo that help to evacuate power from new NPP.	Negotiations still in progress. This project is closely connected wih the project of erection of new line between Rimavska Sobota substation (SK) and Sajoivanka substation (HU); see below.	This cluster will increase the transfer capacity between Slovak and Hungarian network systems and increase security of supply. The internal interconections in Slovakia are necessary for the same objective. Also this cluster is important for support of North - South flow from RES in North of EU.
48	48. 298	Veľký Ďur (SK)	Gabčíkovo (SK)	Erection of new 2x400kV line between two important substations and extension of the substation Veľký Ďur (SK) Line length:93km.					planned	2016	The commissioning date has been moved to earlier term due to ensure security of power evacuation from new NPP in V.ĎUR area.		48
48	48. A125	Veľký Ďur (SK)	Levice (SK)	The erection of new 1x400 kV line between two important Veľký Ďur and Levice substations, including extension of the V.Ďur and Levice substation. The driver for this project is expected connection of to new generation units in Veľký Ďur area.					under consideration	2018	New investment in TYNDP, which will significantly increase of the security and reliability of the power evacuation from new NPP.		48
48	48. A126	Rimavská Sobota (SK)	Sajóivánka (HU)	Connection of the two existing substations (R.Sobota (SK) - Sajoóivánka (HU)) by the new 2x400 kV line (preliminary armed only with one circuit).					under consideration	2016	New investment in TYNDP	Negotiations/bilateral studies in progress. This project is closely connected with the project 2x400kV line Gabčíkovo (SK) - Hungary (see above).	48
48	48. A127	Sajóivánka (HU)	0	Second 400/120 kV transformer and 2x70 Mvar shunt reactors in station Sajóivánka					under consideration	2016	New investment in TYNDP		48
48	48. A128	Győr (HU)	0	Third 400/120 kV transformer and 70 Mvar shunt reactor in station Győr					under consideration	2016	New investment in TYNDP		48
49	49. 235	Tirana(AL)	Pristina (RS)	New 238km 400kV OHL; on 78km the circuit will be installed on the same towers as the Tirana-Podgorica OHL currently in construction (see project 233); the rest will be built as single circuit line.	600	2	5					1	design & permitting	2013	Line in Albania is already constructed. The rest fo the lines develops according to the schedule.		It increases significantly the North to South GTC thus accommodating bulk transports to GR, FYROM and AL
49	49. 236	Leskovac(RS)	Stip (MK)	New 220km 400kV single circuit overhead interconnection between Serbia and FYR of Macedonia. A new 400/110 substation will be built in Serbia between connection nodes.					under construction	Serbian part commissioned, Macedonian part : 2013	Serbian part is completed. Regarding the Macedonian part, the design is finished; the land aquisition is ongoing and the construction tender is in preparation.		49
49	49. 237	TPP Kosovo (RS)	Skopje (MK)	A new 400kV OHL relevant to planning investment of 2000MW of TPP in the area of Kosovo and Metohija. Line length: 85km.					under consideration	2020	Progresses as planned		49
49	49. 252	Melliti (GR)	Kardia (GR)	New 400kV double circuit OHL. Length:40km.					design & permitting	long term	Due to new thermal generation in South Greece the investment is no more needed urgently and postponed to the longer term. (This investment mainly was initially designed to solve voltage problems in South Greece.)		49
49	49. 253	Kardia (GR)	Trikala (GR)	New 400kV double circuit OHL. Length:80km.					design & permitting	long term	Progresses as planned		49
49	49. 254	Larissa(GR)	Trikala (GR)	New 400kV double circuit OHL. Length:57km.					under consideration	long term	Progresses as planned		49
50	50. 238	Pancevo (RS)	Resita (RO)	New 131 km double circuit 400kV OHL between existing substations in Romania and Serbia (63 km on Romanian side and 68 km on Serbian side).	1000	1	3	Area BeLgrade and south Banat region					1	design & permitting	2015 (2019?)	Due to financing gap, the commissioning deadline was postponed to 2019. RO intends to apply for funding through the Operational Programme 'Increase of Economic Competitiveness' - Priority Axis 4. This would ensure realization of the project and allow for faster finalization (2015 instead of estimated 2019). Constructive characteristics were updated as a result of progress of feasibility and design studies.		This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME. / This project increases the transfer capability between Serbia, Romania and accommodates new RES generation on the West/East part of Romanian, respectively Serbia. It also increases the transfer capability on the interface between RO+BG/RS+BA+ME.
50	50. 269	Portile de Fier (RO)	Resita (RO)	New 400kV OHL between existing substation 400 kV Portile de Fier and new 400 kV substation Resita. Line length: 116km. New 400 kV substation Resita, with 400/220 kV and 400/110 kV transformers, as development of the existing 220/110 kV substation.					design & permitting	2016	Constructive characteristics were updated as a result of progress of feasibility and design studies. Commissioning date has been slightly shifted.		50
50	50. A116	Beograd 20 (RS)	0	New 400/110 kV substation on the Belgrade territory					under construction	2012	New investment in TYNDP	By taking large amount of load from other Belgrade substations, the investment will both i/ improve the local SoS significantly, and ii/ relieve the constraints on the EHV local network and enable greater inter-area transits.	50
50	50. A117	Kraljevo 3 (RS)	0	Upgrade of the existing 220/110kV substation Kraljevo 3 by constructing the 400 kV level.					design & permitting	2015	New investment in TYNDP		50
50	50. A118	Kraljevo 3 (RS)	Bajina Basta (RS)	New 140km double circuit 400kV OHL between substation Kraljevo 3 and substation Bajina Basta. Kraljevo 3 (400kV) will be connected to Kragujevac 2 (400 kV) substation, which is connected to a Sofia (Bulgaria) through a 400 kV line.					planned	>2015	New investment in TYNDP	New axis for transits from East to the West, typically from Bulgaria to Bosnia and Montenegro, and further to the west.	50
50	50. 270	Resita( RO)	Timisoara-Sacalaz-Arad (RO)	Upgrade of an existing 220kV double circuit line to 400kV double circuit line and replacemnet of 220 kV substations Timisoara and Sacalaz with 400 kV substations. Line length: 156km.					design & permitting	2022	Due to financing gap, the commissioning deadline was postponed to 2022. Constructive characteristics were updated as a result of progress of feasibility and design studies.		50
51	51. 239	Bitola (MK)	Elbasan (AL)	New 200km cross-border single circuit 400kV OHL between existing substations. New 400/110 kV substation in Ohrid area connected in/out to the new 400 kV line Bitola-Elbasan.	1255 MW BG - AL ,>1000 BG-TR	3	2					1	planned	2015	Change of date of commissioning due to : resolving the problems in the 110KV in S-W Macedonia; facilitate the market integration; increased interest of potential investors.	Selection of consultant for preparation of feasibility study	East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.East-West corridor from Bulgaria to Italy. / Investments 257, 258 and 262 can build up an independant sub-project, as they will both i/ develop alltogether, specifically, grid transfer capability with Turkey; ii/ contributes with all other investments clustered in the project to developping GTC East-West from Bulgaria to BiH and Montenegro.
51	51. 244	Filippi(GR)	Lagadas (GR)	New 400kV substation in Lagadas in Thessaloniki area and connection to the existing substation of Filippi via a new 110km double circuit 400kV OHL.					under construction	2013	Initial delays due to authorization process.The project is now under construction		51
51	51. 256	Maritsa East 1 (BG)	N.Santa (GR)	New interconnection line BG-GR by a 130km single circuit 400kV OHL.					design & permitting	long term	After the interconnection with Turkey, the project can be delayed to LT as it is mainly connected to further RES development. The final commissioning date is subject to change depending of the evolution in the area.		51
51	51. 257	Maritsa East 1 (BG)	Plovdiv (BG)	New 100km single circuit 400kV OHL in parallel to the existing one.					design & permitting	2014	Investments 257,258 and 262 are postponed because the permitting procedures (environmental requirements) with the land owners induced delays .		51
51	51. 258	Maritsa East 1 (BG)	Maritsa East 3 (BG)	New 13km single circuit 400kV OHL in parallel to the existing one.					design & permitting	2014			51
51	51. 262	Maritsa East 1 (BG)	Burgas (BG)	New 400kV OHL. Line length: 150km.					design & permitting	2014			51
52	52. 240	Patras (GR)	400kV Continental System (GR)	New 400kV substation in Patras (GIS Technology) and in&out connection to the existing Axeloos - Distomo 400kV OHL via a new 15km double circuit line, part of which will consist of subsea cable. The project shall constitute the first 400kV corridor to Peloponnese.	600-700	4	1	Peloponnese area					1	design & permitting	2013	The project is likely to be delayed mainly due to the environemental concerns; strong opposition by the local communities resulted in the delay in permitting procedures and subsequent delay in the expected date of commissioning		It increases significantly the GTC to/from the peninula of Peloponnese, thus allowing the accomodation of large amount of RES in the peninsula and also contributes to market integration
52	52. 241	Patras (GR)	Megalopolis (GR)	New 400kV substation in Megalopolis and connection to Patras 400kV substation via a 110km double circuit OHL. 2nd corridor to Peloponnese.					design & permitting	2013			52
52	52. 242	Megalopolis (GR)	Korinthos (GR)	Construction of a new 400kV substation in Korinthos (GIS Technology) and connection to the Megalopolis substation via a 110km double circuit 400kV OHL.					design & permitting	2014			52
52	52. 243	Korinthos (GR)	Koymoyndoyros (GR)	Replacement of the existing 150kV double circuit line by a 87km double circuit 400kV OHL.					design & permitting	2014			52
53	53. 276	Suceava(RO)	Gadalin(RO)	New 400kV OHL between existing stations. Line length: 260km.	2000-2500	4	1					2	planned	2021	Constructive design characteristics and time schedule were updated as a result of progress of feasibility and design studies.		The project will help evacuate important amount of new generation (wind +nuclear generation) in Eastern part of Romania
53	53. A131	Stejaru(RO)	Gheorghieni(RO)	Reconductoring (with HTLS) of existing simple circuit 220kV line.					under consideration	2015	New investment in the TYNDP, required to integrate new RES generation and maintain the GTC for the entire project.		53
53	53. 273	Cernavoda (RO)	Stalpu	New 400kV double circuit OHL between existing stations. Line length:145km.					planned	2017	Constructive characteristics were updated as a result of progress of feasibility and design studies.		53
53	53. 274	Constanta (RO)	Medgidia(RO)	New 400kV double circuit (one circuit wired) OHL between existing stations. Line length:75km.					planned	2020	As for other investments, the commissioning date was postponed due to financing gap. Constructive characteristics were updated as a result of progress of feasibility and design studies.		53
53	53. 275	Smardan(RO)	Gutinas(RO)	New 400kV double circuit OHL between existing stations. Line length:140km.					planned	2020	As for other investments, the commissioning date was postponed due to financing gap. Constructive characteristics were updated as a result of progress of feasibility and design studies.		53
53	53. 271	connection IN-OUT in Medgidia(RO) of actual 400kV OHL Isaccea(RO)-Varna (BG)	0	The 400kV Isaccea (RO) - Varna (BG) is passing near 400 kV substation Medgidia S. The line shall be connected in Medgidia S, through a double circuit OHL. New wind farms shall be connected to the 400 kV OHL Isaccea - Medgidia S section . Substation Medgidia S, 400 kV, shall be refurbished with GIS technology in order to provide necessary space for new connections.					design & permitting	2015	As for other investments, the commissioning date was postponed due to financing gap. Constructive characteristics were updated as a result of progress of feasibility and design studies.		53
53	53. A132	Stalpu (RO)	Teleajen (RO) - Brazi (RO)	Upgrade of an existing 220kV single circuit line to 400kV. New 400 kV substations: Stalpu (400/110kV, 1x250 MVA), Teleajen (400/110kV, 1x400 MVA)					planned	2018	New investment in TYNDP	This investment was merged with investment 273 in TYNDP 2010. They are now presented as separate investments in TYNDP 2012, according to internal project organization. The network development is still the same.	53
53	53. A133	Fantanele (RO)	Ungheni (RO)	Reconductoring (with HTLS) of existing simple circuit 220kV line.					under consideration	long term	New investment in the TYNDP, required to accomodate new RES generation not foreseen in the TYNDP 2010, by increasing the GTC for the entire project.		53
53	53. 272	Medgidia (RO)	0	Connection IN-OUT in Medgidia (RO) of existing 400kV OHL Isaccea (RO)-Dobrudja (BG), passing nearby. The line shall be connected in Medgidia S, through a double circuit OHL. Substation Medgidia S, 400 kV, shall be refurbished with GIS technology in order to provide necessary space for new connections.					design & permitting	2015	As for other investments, the commissioning date was postponed due to financing gap. Constructive characteristics were updated as a result of progress of feasibility and design studies.	New wind farms shall be connected to the 400 kV OHL Isaccea - Medgidia S section.	53
53	53. A134	Gheorghieni(RO)	Fantanele (RO)	Reconductoring (with HTLS) of existing simple circuit 220kV line.					under consideration	2015	New investment in the TYNDP, required to accomodate new RES generation not foreseen in the TYNDP 2010, by increasing the GTC for the entire project.		53
54	54. 293	Voľa (SK)	point of splitting (SK)	Splitting of the existing single 400kV line between Lemešany and Veľké Kapušany substations to connect the new 400kV substation Voľa with transformation 400/110kV (replacing existing 220kV substation). New 400kV double circuit OHL. Length: 23km	500	2	2					1	design & permitting	2013	Progresses as planned		This cluster will increase the transfer capacity between Slovak and Hungarian network systems and increase security of supply. The internal interconections in Slovakia are necessary for the same objective. Also this cluster is important for support of North - South flow from RES in North of EU.
54	54. 294	Lemešany (SK)	Veľké Kapušany (SK)	Erection of new 400 kV line between Lemešany and Veľké Kapušany substations. The project includes the extension both substations Lemešany and V.Kapušany. Line length:100 74km.					planned	2018	Progresses as planned		54
54	54. A127	Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK) / Veľké Kapušany (SK)	tbd (HU)	Erection of new 2x400 line between SK and Hungary (substation on Hungarian side still to be defined)					under consideration	2021	New investment in TYNDP		54
55	55. 302	Vyskov (CZ)	Cechy stred (CZ)	New second circuit 400kV OHL; 1385 MVA.	3000	5	5	Prague area					1	design & permitting	2015	Progresses as planned		This project is required both to ease power flows West to East and to enhance security of supply of Prague.
55	55. 303	Babylon (CZ)	Bezdecin (CZ)	New second circuit 400kV OHL; 1385 MVA.					planned	2016	Progresses as planned		55
55	55. 304	Babylon (CZ)	Vyskov (CZ)	New second circuit 400kV OHL; 1385 MVA.					planned	2018	Progresses as planned		55
55	55. A91	Praha Sever (CZ)	0	New 400/110kV substation equipped with transformers 2x350MVA .					planned	long term	New investment in TYNDP		55
55	55. 310	Vyskov (CZ)	Reporyje (CZ)	New connection between 2 existing substations line single circuit OHL 1385 MVA.					under consideration	long term	Schedule harmonization with other priority investments: this investment has been delayed because of priority given to other investments		55
56	56. A92	Chodov (CZ)	Cechy stred (CZ)	Adding second circuit to existing single circuit line OHL upgrade in length of 35.1km. Target capacity 2x1385 MVA.	1000	5	5					1	planned	2021	New investment in TYNDP		This project is required both to ease power flows West to East and for future generation evacuation.
56	56. A93	Tynec (CZ)	Krasikov (CZ)	Adding second circuit to existing single circuit line OHL upgrade in length of 103.8km. Target capacity 2x1385 MVA.					planned	2025	New investment in TYNDP		56
57	57. 320	Dargoleza (PL)	0	A new AC 400/110kV (450 MVA) substation between existing substations Słupsk and Żarnowiec in Northern Poland. New substation Dargoleza is connected by splitting and extending of existing 400kV line Słupsk - Dargoleza.	3000	4	1					2	planned	2020	The new substation Dargoleza is required for the connection new wind generation in Northern Poland. The time horizon for comissioning of this investment has been changed due to change in wind farms connection schedule in the region.		Wind – the infrastructure in this project assures reliable connection of 3000 MW of wind generation in northern Poland. It also allows the evacuation of power in the southern direction.
57	57. 328	Piła Krzewina (PL)	Bydgoszcz Zachód (PL)	New 84km 400kV double circuit 2x1870 MVA OHL interconnection line Piła Krzewina - Bydgoszcz Zachód temporarily on 220kV.					design & permitting	2016	The time schedule of the project was shifted to meet the schedule of the RES (wind) generation connection. This one year delay in the plans appeared after updating of the NDP. The change in the NDP introduced a double circuit.		57
57	57. 329	Żydowo (PL)	Słupsk (PL)	A new AC 400/110kV substation next to existing 220/110kV substation in Northern Poland with transformation 400/110kV 450 MVA. New substation Żydowo is connected by new 70km 400kV 2x1870 MVA OHL double circuit lines Żydowo - Słupsk and Żydowo - Gdańsk Przyjaźń. Dismantling of existing 220/110kV transformers + Upgrade of substation SŁupsk					planned	2020	The date of commissioning evolved due to regulatory, social and environmental issues. The investment also foresee upgrade works in substation Słupsk.		57
57	57. 330	Żydowo (PL)	Gdańsk Przyjaźń (PL)	A new AC substation in Gdańsk Agglomeration Area. New substation Gdańsk Przyjaźń is connected by splitting and extending of one circuit of existing line Żarnowiec - Gdańsk Błonia and new 150km 400kV 2x1870 MVA double circuit OHL line Żydowo - Gdańsk Przyjaźń with one circuit from Żydowo to Gdańsk temporarily on 220kV after dismantling of 220kV line Żydowo - Gdańsk.					planned	2020	The date of commissioning evolved due to regulatory, social and environmental issues.		57
57	57. 352	Dunowo (PL)	Plewiska (PL)	Construction of a new double circuit 400kV OHL Dunowo - Żydowo (2x1870 MVA) partly using existing 220kV line + Construction of a new 400kV OHL Plewiska - Piła Krzewina - Żydowo (2x1870 MVA); single circuit temporarily working as a 220kV + A new AC 400kV switchgear in existing substation Pila Krzewina + upgrade of substation Dunowo					design & permitting	2020	Progressed as planned. The investment also foresee upgrade works in substation Dunowo.		57
58	58. 353	Krajnik (PL)	Baczyna (PL)	Construction of a new double circuit 400kV OHL Krajnik - Baczyna (2x1870 MVA, 91km); single circuit temporarily working at 220kV on Krajnik - Gorzów part + New substation 400kV Baczyna will be connected by splitting and extending existing line Krajnik-Plewiska + Upgrading of limitations line Krajnik - Plewiska.	>1000	1	2					2	planned	2020	Progresses as planned		Bridge – third interconnection between Poland and Germany.
58	58. 355	Mikułowa (PL)	Świebodzice (PL)	Double circuit line 220kV Mikułowa-Świebodzice will be upgraded to 400kV - single circuit temporarily working at 220kV.					planned	2020	Progresses as planned		58
58	58. A67	Gubin (PL)	0	New 400 kV substation planned near the PL-DE border. The substation will be connected to planned line Eisenhüttenstadt (DE) - Plewiska (PL) creating new lines Eisenhüttenstadt (DE) - Gubin (PL) and Gubin (PL) - Plewiska (PL).					planned	2020	New investment in TYNDP	This new substation on the third DE-PL connection is necessary for future generation connection while ensuring interconnection capability.	58
58	58. 140	Eisenhüttenstadt (DE)	Plewiska (PL)	New 400kV double circuit OHL Eisenhüttenstadt (DE) - Plewiska (PL) including the construction of new substation Plewiska Bis (PL)					planned	2020	Progresses as planned		58
59	59. 368	Ełk (PL)	PL-LT border (LT)	Construction of a new 400kV OHL Ełk to PL-LT border. (2x1870 MVA, 108km).	1000	1	5	South LT and NE/central PL					3	design & permitting	2015	Progresses as planned		“LitPol Link” project. Interconnection of Lithuanian power system with Polish power system via Back to Back station. This project allows integration of Baltics to the internal European power market,
59	59. 369	Siedlce Ujrzanów (PL)	Miłosna (PL)	Construction of a new 400kV OHL Siedlce Ujrzanów - Miłosna (1870 MVA, 84km) + A new AC 400kV switchgear in existing substation Siedlce Ujrzanow with transformation 400/110kV 400 MVA.					design & permitting	2015	Progresses as planned		59
59	59. 370	Ełk (PL)	Łomża (PL)	Construction of a new 400kV double circuit OHL Ełk - Łomża (2x1870 MVA, 95km) + A new AC 400kV switchgear in existing substation Elk + A new 400 kV AC substation Łomża					design & permitting	2015	Łomża has been elected as end substation for the project and the technical description is adapted accordingly. Progresses as planned otherwise.		59
59	59. 371	Ostrołęka (PL)	Narew (PL)	Construction of a new 400kV OHL Ostrołęka-Łomża-Narew (1870 MVA, 120km) + A new AC 400kV switchgear in existing substation Ostroleka (in two stages) with transformation 400/220kV 500 MVA and with transformation 400/110kV 400 MVA + extension of 400 switchgear in substation Narew.					design & permitting	2015	Progressed as planned. The investment also foresee extension works in substation Narew.		59
59	59. 372	Oltarzew (PL)	0	A new AC substation with two transformers 400/220kV 2x500 MVA and one 400/110kV 330 MVA will be connected by splitting 400kV line Rogowiec-Miłosna and Miłosna-Płock and 220kV line Mory-Sochaczew and Mory-Janów.					under construction	2015	Progresses as planned		59
59	59. 373	Ostrołęka (PL)	Stanisławów (PL)	Single circuit line 220kV Ostrołęka-Miłosna will be partly upgraded to double circuit line 400kV (2x1870 MVA, 106km) with development of Ostrołęka 400kV substation + New substation 400kV Stanisławów will be connected by splitting and extending existing line Miłosna-Narew and Miłosna-Siedlce.					design & permitting	2020	Progresses as planned		59
59	59. 374	Kozienice (PL)	Siedlce Ujrzanów (PL)	Existing single circuit line will be upgraded to 400kV line in the same direction (1870 MVA, 90km) + upgrade of Kozienice substation to connect the new line					design & permitting	2020	Progressed as planned. The investment also foresee extension works in substation Kozienice		59
59	59. 375	Płock (PL)	Olsztyn Mątki (PL)	New single circuit line 400kV (1870 MVA, 180km) with development of Olsztyn Mątki 400kV substation.					design & permitting	2020	Progresses as planned		59
59	59. 376	Alytus (LT)	PL-LT border (PL)	Construction of Back-to-Back convertor station near Alytus 330kV substation. Construction of double circuit 400kV OHL between Alytus and PL-LT border. Construction of 330kV AC line Alytus-Kruonis. Length of line: 46km.					design & permitting	2015	Progresses as planned		59
59	59. 379	Kruonis (LT)	Alytus (LT)	New double circuit 330kV OHL (2x1080 MVA, 53km).					planned	2015	Progresses faster than intially planned to support the LitPol project		59
60	60. 377	Klaipeda (LT)	Telsiai (LT)	New single circuit 330kV OHL (943 MVA, 85km).	700	3	3	West LV region					2	under construction	2014	Project delayed because of land renting issues.		“Nordbalt“ project. Planned DC connection between Lithuania and Sweden. The project will connect the Baltic grid to the Nordic and integrate the Baltic countries with the Nordic electricity market, increases security of supply. Possibility to connect offshore wind farms as well.
60	60. 378	Panevezys (LT)	Musa (LT)	New single circuit 330kV OHL (1080 MVA, 80km).					planned	2018	Project postponed after investment portfolio optimisation		60
60	60. 383	Klaipeda (LT)	Nybro (SE)	(NordBalt) A new 300kV HVDC VSC partly subsea and partly underground cable between Lithuania and Sweden. (440km).					design & permitting	2015	Progresses as planned		60
60	60. 384	RigaCHP1 (LV)	Imanta (LV)	A new 12.5km AC 330kV cable will be built from RigaCHP1 substation to Imanta substation. Both substations will be reconstructed, according new line connecting. New cable will be underground and one part will be underwater (under Daugava river). Expected capacity: 880MW.					under construction	2012	Progresses as planned	The investment contributes also to project 62	60
60	60. A52	Ekhyddan (SE)	Nybro/Hemsjö (SE)	New single circuit 400 kV OHL					under consideration	2019	New investment in TYNDP		60
60	60. 385	Grobina (LV)	Imanta (LV)	Kurzeme roject a Latvian grid reinforcement roject with new 330kV OHL construction and connection to the Riga node. New 330kV OHL construction mainly instead of the existing 110kV double circuit line route, 110kV line will be renovated at the same time and both will be assembled on the same towers. Length 380km, Capacity 800MW					design & permitting	2018	Invesetment delays due to authorization processand the extensive works.	The investment contributes also to project 62	60
61	61. 380	Visaginas (LT)	Kruonis (LT)	New single circuit 330kV OHL (1080 MVA, 200km).	1400	4	5					1	planned	2020	Progresses as planned		“New NPP” project. Grid development for connection of new Lithuanian nuclear power plant planned in Visaginas to the power system. This project allows safe and reliable integration of new NPP to the power system.
61	61. 381	Visaginas (LT)	Liksna (LV)	Upgrade single circuit OHL (943 MVA, 50km).					under consideration	2020	Progresses as planned		61
61	61. 382	Vilnius (LT)	Neris (LT)	New single circuit 330kV OHL (943 MVA, 50km).					planned	2020	Progresses as planned		61
62	62. 60. 384	0	0	0	450-600	1	1	Riga reagion					1	0	0	0	The investment contributes both to project 62 and project 64. For the technical description see project 62	This project will increase the transfer capability between Estonia and Latvia and will accommodate RES generation in the Baltic Sea. This will be the 3rd corridor between these countries.
62	62. 60. 385	0	0	0					0	0	0	The investment contributes both to project 62 and project 64. For the technical description see project 62	62
62	62. 386	Kilingi-Nomme(EE)	RigaCHP2(LV)	Estonia-Latvia third interconnection will consist of 330 kV AC OHL Harku-Lihula-Sindi in Estonian part and OHL between Kilingi-Nõmme substation in Estonia and TEC2 substation in Latvia. The third interconnection allows to increase the NTC between Estonia and Latvia additionally in the range of 450 to 600 MW .					planned	2020	Progresses as planned		62
62	62. 387	Tartu (EE)	Sindi (EE)	A new 162km internal connection will be established on existing route resulting in double circuit line with 2 different voltages (330kV / 110kV).					under construction	2014	Progresses as planned		62
62	62. 388	Harku (EE)	Sindi (EE)	New double circuit OHL with 2 different voltages 330 kV and 110 kV and with capacity 1200 MVA/240 MVA and a length 140 km. Major part of new internal connection will be established on existing right of way on the Western part of Estonian mainland.					design & permitting	2018	Progresses as planned		62
63	63. 389	Eesti (EE)	Püssi (EE)	Reinforcement of existing 57km single circuit 330kV OHL. Expected capacity:1200 MVA.	650	3	2	NW Estonia					2	completed	commissioned	Commissioned		Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.Estlink2 ; The main driver for this cluster is integration need of Electricity Market. / This project will increase the transfer capability between Estonia and Finland and will accommodate RES generation in the North of Estonia and will increase the SOS in the Baltics.
63	63. 390	Balti (EE)	Püssi (EE)	Reconstruction of 68km single circuit 330kV OHL.					completed	commissioned	Commissioned		63
63	63. 391	Püssi (EE)	Anttila (FI)	A new HVDC (450kV) connection will be built between Estonia and Finland. On the Finnish side, a 14km DC overhead line will be built to a new substation Anttila where the converter station will be placed. On the Estonian side, a 11km DC cable line will be built to a existing substation Püssi where the converter station will be placed. length of marine cable is 140km. Expected capacity: 650MW.					under construction	2014	The expected date of commissioning is beginning of 2014, postponed a few months compared to the preliminary estimate end of 2013.		63
64	64. 392	Yllikkälä (FI)	Huutokoski (FI)	New 155km single circuit 400kV OHL and renovation of 400kV substations in Yllikkälä and Huutokoski. Expected capacity: 1850 MVA.	700-1400	3	2	West coast Finland					1	under construction	2013	Progresses as planned. Expected date of commission is beginning of 2013.		Several 400 kV AC lines are planned in Finland to be built to increase the North-South transmission cpacity thus enabling the integration of new renewable and conventional generation in northern finland and to compensate the dismantling of the obsolescent exixting 220 kV lines. The commissioning of the lines is scheduled to take place in segments both in mid and long term.
64	64. 393	Seinäjoki Ulvila Ventusneva (FI)	Tuovila (FI) Kristinestad (FI) Pyhänselkä (FI)	Four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. Commissioning of first section in year 2011, second in 2014 third in ca. 2018 and fourth ca 2020. total length of lines: 520 km. Expected capacity: 1850 MVA.					under construction	2011/2020	Project has progressed as planned. Since TYNDP 2010 Seinäjoki-Tuovila has been constucted and Ulvila-Kristinestad has progressed to design and permitting phase. Keminmaa-Pyhänselkä is now presented as a separate investment item.		64
64	64. A62	Pyhänselkä (FI)	Petäjävesi or Vihtavuori (FI)	New single circuit 400 kV OHLs will be built from middle Finland to Oulujoki Area to increase the capacity between North and South Finland.					design & permitting	2020	New investment in TYNDP		64
65	65. 394	Hikiä (FI)	Forssa (FI)	New 80km single circuit 400kV OHL and building of 400 kV substation in Forssa.	800	2	4	SW Finland					1	design & permitting	2015	Progresses as planned		Reinforcements due to changed exchange patterns and reliable grid operation of South-West Finland.
65	65. A63	Forssa (FI)	Lieto (FI)	New 67km single circuit 400 kV OHL.					under consideration	2017	New investment in TYNDP
66	66. 400	Ekhyddan (SE)	Barkeryd (SE)	New single circuit 400kV OHL.	1250	4	1					2	design & permitting	2017	Progresses as planned		The new subsea connection to the island of Gotland will be two connections with a capacity of 500 MW for each cable.
66	66. 401	Västervik (SE)	Gotland (SE)	New DC subsea cable interconnection 400kV (1000 MW).					design & permitting	2017 -2020	The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES. / The first cable is progressing as planned but the second cable is planned to be in commission after 2017 due to adjustments to RES.	The new subsea connection to the island of Gotland will be two connections with a capacity of 500 MW for each cable. The first cable is planned to be in commission 2017 and the second is planned to be in commission between 2018 and 2020.	66
67	67. 402	Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)Barkeryd (SE) / Hallsberg (SE)	Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE) / Tveiten (NO) / Hurva (SE)	"South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW."South West link" / consisting of three main parts: / 1) New 400kV line between Hallsberg and Barkeryd (SE) / 2) New double HVDC VSC underground cable and OHL between Barkeryd and Hurva (SE) / 3) New double HVDC VSC line between Barkeryd (SE) and Tveiten (NO). / The project also include new substations and converter stations in the connection points line / double circuit new OHL Hallsberg - Barkeryd 170km, underground VSC Barkeryd - Hurva 250km and VSC Barkeryd - Tveiten with 103km on the Norwegian side. Expected capacity: 1200MW.	1400 (E-W), 1200 (N-S)	3	2					3	design & permitting	2014-2019	Commissioning date updated after bilateral negociations between the two countries. Hallsberg-Barkeryd-Hurva expected in 2014; Barkeryd-Tveiten in 2019		5 investments of HVDC and AC lines in Sweden and Norway as well as between the countries, resulting in increased GTC and market integration
67	67. 411	Rød (NO)	Sylling (NO)	Voltage upgrading of existing single circuit 300kV OHL Rød-Tveiten-Flesaker-Sylling in connection with the new HVDC line to Sweden, the Syd Vest link.					design & permitting	2018/2020	Investment postponed, especially because of long permitting processes.		67
67	67. 412	Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) - Rød (NO) - / Sylling (NO) - / Flesaker (NO) -	Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)Hasle (NO) / Tegneby (NO) / Tegneby (NO)	Reinvestment and capacity increase Oslofjord 400kV subsea cables. Three cables: Filtvedt - Brenntangen, Solberg - Brenntangen, and Teigen - Evje.					design & permitting	2015	Investment delayed, especially because of long permitting processes. One cable is under construction.		67
68	68. 421	Ofoten (NO)	Balsfjord (NO)	New 160km single circuit 400kV OHL.	350-1500	2	1	Northern Norway					2	design & permitting	2016	Investment delayed, especially because of long permitting processes.		The main purpose of this project is to secure the norther part of NO.
68	68. 422	Balsfjord (NO)	Hammerfest (NO)	New 360 km single circuit 400kV OHL.					design & permitting	2018	Investment delayed, especially because of long permitting processes.
68	68. 423	Skaidi (NO)	Varangerbotn (NO)	New 230 km single circuit 400kV OHL.					planned	2022	Investment postponed, especially because of long permitting processes.
69	69. 424j	Bramford (GB)	Twinstead (GB)	New 400kV double circuit	2600	4	1					2	Design & Permitting	2018/2019	Delayed by one year to 2018/19 due to an anticipated slower growth in the uptake of wind.		This project supports the evcaution of energy from a new nuclear power plant and from the offshore wind parks of the Eastern coast of GB.
69	69. A39	Sizewell C (GB)	Bramford (GB)	Reconductor Sizewell C-Bramford-Sizewell	1800					Planned	2015/16	New investment in TYNDP, answering an expected growth in offshore wind and nuclear generation in and around Norfolk and East Anglia, above what was anticipated for the TYNDP 2010.		69
69	69. A40	Norwich Main (GB)	Bramford (GB)	Norfolk Offshore Wind: NORW-BRFO Tee-in to Lowestoft					Planned	2015/16	New investment in TYNDP, answering an expected growth in offshore wind and nuclear generation in and around Norfolk and East Anglia, above what was anticipated for the TYNDP 2010.		69
69	69. A41	Walpole (GB)	Bramford (GB)	Reconductoring Norwich Main-Walpole and Bramford-Norwich Main					Under Construction	2015/2016	New investment in TYNDP, answering an expected growth in offshore wind and nuclear generation in and around Norfolk and East Anglia, above what was anticipated for the TYNDP 2010.		69
70	70. 405	Kristiansand (NO)	Rød (NO)	Voltage upgrading of an existing single circuit 300kV OHL and a new section of OHL between Rød and Bamle. Total length: 175km.	700	5	2					2	design & permitting	2014	Progresses as planned		Market integration and RES integration.
70	70. 426	Kristiansand (NO)	Tjele (DK)	Skagerak 4: 4th HVDC connection between Southern Norway and Western Denmark, built in parallel with the existing 3 HVDC cables; new 700MW including 230km 500kV DC subsea cable.					Under construction	2014	Progresses as planned		70
71	71. 427	Endrup (DK)	Eemshaven (NL)	COBRA: New single circuit HVDC connection between Jutland and the Netherlands via 350km subsea cable; the DC voltage will be up to 320kVand the capacity 600-700MW.	700 MW	5	2					2	design & permitting	2016	Progresses as planned		Cobra
72	72. 430	Revsing (DK)	Landerupgård (DK)	New 18km single circuit 400kV line via cable with capacity of approx. 1200 MW.	950	4	1	DK west and north DE					2	Planned	2017	Progresses as planned		The main purpose of the project is to integrate and transmit large scale wind power in DK west.
72	72. 435	Endrup (DK)	Revsing(DK)	Upgrade of 50km double-circuit 400kV OHL to reach a capacity of approx. 2000MW.					design & permitting	2015	Earlier date of commissioning than initially expected caused by reprioritization of project. Also one of the substations has been changed: Endrup was replaced by Tjele.		72
72	72. 436	Idomlund (DK)	Endrup (DK)	New 74km single circuit 400kV line via cable with capacity of approx. 1200MW.					under consideration	2018/2020	Envisaged route changed from Idomlund-Tjele to Idomlund-Endrup		72
73	73. 432	Asvæsværket (DK)	Kyndbyværket (DK)	New 60km single circuit 400kV line via cable with capacity of approx. 1200 MW.	>1000	4	4					1	design & permitting	2014	Progresses as planned		The project will increase the stability of the DK eastern power system and allow for larger transmission and transit.
73	73. 433	Glentegård (DK)	Amagerværket & H.C. Ørstedværket (DK)	New 22km single circuit 400kV line via cable with capacity of approx. 1200MW.					planned	2016	Progresses as planned		73
74	74. 443	Richborough (GB)	Zeebrugge (BE)	Nemo Project: New DC sea link including 135km of 250kV DC subsea cable with 1000MW capacity	>1000	1	2	Thames estuar					2	Planned	2018	Investment delayed to 2018 due to authorization delays related to needed internal grid reinforcements	Nemo project	Interconnection between UK and the mainland Europe(BE).
74	74. 449	Richborough (GB)	Canterbury (GB)	New 400kV double circuit OHL and new 400kV substation in Richborough					Planned	2019/2020	Progresses as planned	The reinforcements shown here reflect initial options but are subject to consultation and review of other feasible options.	74
74	74. 450	Sellindge (GB)	Dungeness (GB)	Reconductor Sellindge-Dungeness					Planned	2014/2015	The reconductoring of the Sellindge to Dungeness circuits (Project 450) remain as originally planned in the TYNDP 2010.		74
75	75. 444	Zomergem (BE)	Zeebrugge (BE)	New approx 50km double-circuit 380kV ( 3000MVA for each circuit) between Zomergem and Zeebrugge to evacuate the locally (offshore) produced power line and allow connection of NEMO to 380 kV grid.	1500	4	1					2	design & permitting	2014	Progresses as planned	Stevin project	The project allows the connection of 2,3 GW of offshore wind production. It also allows onshore RES connection. This project enhances security of supply of Belgian coastal area and allows the NEMO connection.
75	75. A28	Zeebrugge (BE)	offshore platform (BE)	2 offshore platforms connected to AC grid with underground cables including compensation					planned	2016	New investment in TYNDP, resulting from recent studies demonstrating such a platform would be optimal for Belgian offshore wind offtake. Planning and implementation of the project depends on the evolution of Belgian legislation.	Belgian offshore platform	75
76	76. A42	Pelham (GB)	Waltham Cross (GB)	Reconductor Pelham-Rye House-Waltham Cross	7600	4	1	London area					3	Design & Permitting	2015/2016	New investment in TYNDP	New projects in the London area, not previously reported in the TYNDP 2010. All of these investments are required due to a combination of age related asset replacement, increasing power flows and changing customer demand connection requirements. A further driver for all of these projects is that power flows through London increase during interconnector export to mainland Europe (Power flows from the north through London to the interconnectors within the Thames Estuary).	All of these investments are required due to a combination of age related asset replacement, increasing power flows and changing customer demand connection requirements. A further driver for all of these projects is that power flows through London increase during interconnector export to mainland Europe (Power flows from the north through London to the interconnectors within the Thames Estuary).
76	76. A43	Hackney (GB)	Waltham Cross (GB)	Uprate to 400kV Hackney-Tottenham-Waltham Cross					Design & Permitting	2015/2016	New investment in TYNDP		76
76	76. A44	Hackney (GB)	St. John's Wood (GB)	New 400kV St. John's Wood-Hackney double circuit					Design & Permitting	2017/2018	New investment in TYNDP		76
76	76. A45	Tilbury (GB)	Elstree (GB)	Uprate to 400kV Tilbury-Warley-Elstree					Planned	2021/22	New investment in TYNDP		76
76	76. A46	St. John's Wood (GB)	Wimbledon (GB)	New 400kV St. John's Wood-Wimbledon cables					Design & Permitting	2017/2018	New investment in TYNDP		76
76	76. A47	West Weybridge (GB)	Beddington (GB)	Uprate to 400kV West Weybridge-Chessington-Beddington					Planned	2017/2018	New investment in TYNDP		76
77	77. 452	Deeside (GB)	Hunterston (GB)	New 2000MW HVDC Link via 360km 500kV DC subsea cable on the West Coast of the UK and new 400kV substation in Deeside	4000	4	1					3	Design & Permitting	2015/2016	Progresses as planned (still targetting the financial year 2015/2016)		This project facilitates the connection of RES and the connection of the remote Scottish Islands.
77	77. 453	Peterhead (GB)	Hawthorn Pit (GB)	New 2000MW HVDC Link via 365km 500kV DC subsea cable on the East Coast of the UK and new 400kV substation in Hawthorn Pit					Planned	2018/2019	Progresses as planned (still targetting the financial year 2018/2019)		77
77	77. 454	Hawthorn Pit (GB)	Norton (GB)	Uprate to 400kV Hawthorn Pit-Norton					Planned	2018/2019	Progresses as planned (still targetting the financial year 2018/2019)		77
77	77. 456	Harker (GB)	Quernmore (GB)	Reconductor Harker-Hutton-Quernmore					Design & Permitting	2014/2015	Progresses as planned (still targetting the financial year 2014/2015)		77
77	77. 449a	Gravir (GB)	Beauly (GB)	Western Isles link. New 450MW HVDC link, +/- 150kV. Route length 156km (80km subsea, 76km onshore underground cable).					design & permitting	2015	The 2010 TYNDP showed commissioning scheduled for 2013. However the developers of the large Western Isles windfarm projects which drive the need for the link, have experienced commercial delays. Commissioning of the link is therefore now projected for 2015.		77
77	77. 450a	Kergord and Caithness (GB)	Blackhillock (GB)	The Moray Firth HVDC development - Shetland and Caithness links with offshore HVDC hub. Three ended HVDC link, 2 x 600MW legs and common 1200MW leg. Total route length 395km.					design & permitting	2016	Projected commissioning is now 2016. The 2010 TYNDP showed commissioning scheduled for 2014. At that time the concept was to include an offshore node in a subsea HVDC link that was planned from Shetland to the Scottish mainland. That link was being designed to connect the Viking Energy windfarm project on Shetland. The Shetland link was termed the Base Project and the node was referred to as Incremental Works. / The node would receive a connection from Caithness in 2016 for the export of renewables from that region and would also offer the potential for connection of adjacent offshore windfarms. However, the Viking project suffered consenting delays, and so late in 2010 the Caithness to Moray HVDC link was re-designated as the Base Project into which the node would be incorporated. The achievable timetable for the Caithness leg with commissioning in 2016 then became the timetable for the investment. / Projected commissioning is now 2016. The 2010 TYNDP showed commissioning scheduled for 2014. At that time the concept was to include an offshore node in a subsea HVDC link that was planned from Shetland to the Scottish mainland. That link was being designed to connect the Viking Energy windfarm project on Shetland. The Shetland link was termed the Base Project and the node was referred to as Incremental Works. / The node would receive a connection from Caithness in 2016 for the export of renewables from that region and would also offer the potential for connection of adjacent offshore windfarms. However, the Viking project suffered consenting delays, and so late in 2010 the Caithness to Moray HVDC link was re-designated as the Base Project into which the node would be incorporated. The achievable timetable for the Caithness leg with commissioning in 2016 then became the timetable for the investment. / Projected commissioning is now 2016. The 2010 TYNDP showed commissioning scheduled for 2014. At that time the concept was to include an offshore node in a subsea HVDC link that was planned from Shetland to the Scottish mainland. That link was being designed to connect the Viking Energy windfarm project on Shetland. The Shetland link was termed the Base Project and the node was referred to as Incremental Works. / The node would receive a connection from Caithness in 2016 for the export of renewables from that region and would also offer the potential for connection of adjacent offshore windfarms. However, the Viking project suffered consenting delays, and so late in 2010 the Caithness to Moray HVDC link was re-designated as the Base Project into which the node would be incorporated. The achievable timetable for the Caithness leg with commissioning in 2016 then became the timetable for the investment. / Projected commissioning is now 2016. The 2010 TYNDP showed commissioning scheduled for 2014. At that time the concept was to include an offshore node in a subsea HVDC link that was planned from Shetland to the Scottish mainland. That link was being designed to connect the Viking Energy windfarm project on Shetland. The Shetland link was termed the Base Project and the node was referred to as Incremental Works. / The node would receive a connection from Caithness in 2016 for the export of renewables from that region and would also offer the potential for connection of adjacent offshore windfarms. However, the Viking project suffered consenting delays, and so late in 2010 the Caithness to Moray HVDC link was re-designated as the Base Project into which the node would be incorporated. The achievable timetable for the Caithness leg with commissioning in 2016 then became the timetable for the investment. / Projected commissioning is now 2016. The 2010 TYNDP showed commissioning scheduled for 2014. At that time the concept was to include an offshore node in a subsea HVDC link that was planned from Shetland to the Scottish mainland. That link was being designed to connect the Viking Energy windfarm project on Shetland. The Shetland link was termed the Base Project and the node was referred to as Incremental Works. / The node would receive a connection from Caithness in 2016 for the export of renewables from that region and would also offer the potential for connection of adjacent offshore windfarms. However, the Viking project suffered consenting delays, and so late in 2010 the Caithness to Moray HVDC link was re-designated as the Base Project into which the node would be incorporated. The achievable timetable for the Caithness leg with commissioning in 2016 then became the timetable for the investment. / Projected commissioning is now 2016. The 2010 TYNDP showed commissioning scheduled for 2014. At that time the concept was to include an offshore node in a subsea HVDC link that was planned from Shetland to the Scottish mainland. That link was being designed to connect the Viking Energy windfarm project on Shetland. The Shetland link was termed the Base Project and the node was referred to as Incremental Works. / The node would receive a connection from Caithness in 2016 for the export of renewables from that region and would also offer the potential for connection of adjacent offshore windfarms. However, the Viking project suffered consenting delays, and so late in 2010 the Caithness to Moray HVDC link was re-designated as the Base Project into which the node would be incorporated. The achievable timetable for the Caithness leg with commissioning in 2016 then became the timetable for the investment. / Projected commissioning is now 2016. The 2010 TYNDP showed commissioning scheduled for 2014. At that time the concept was to include an offshore node in a subsea HVDC link that was planned from Shetland to the Scottish mainland. That link was being designed to connect the Viking Energy windfarm project on Shetland. The Shetland link was termed the Base Project and the node was referred to as Incremental Works. / The node would receive a connection from Caithness in 2016 for the export of renewables from that region and would also offer the potential for connection of adjacent offshore windfarms. However, the Viking project suffered consenting delays, and so late in 2010 the Caithness to Moray HVDC link was re-designated as the Base Project into which the node would be incorporated. The achievable timetable for the Caithness leg with commissioning in 2016 then became the timetable for the investment. / Projected commissioning is now 2016. The 2010 TYNDP showed commissioning scheduled for 2014. At that time the concept was to include an offshore node in a subsea HVDC link that was planned from Shetland to the Scottish mainland. That link was being designed to connect the Viking Energy windfarm project on Shetland. The Shetland link was termed the Base Project and the node was referred to as Incremental Works. / The node would receive a connection from Caithness in 2016 for the export of renewables from that region and would also offer the potential for connection of adjacent offshore windfarms. However, the Viking project suffered consenting delays, and so late in 2010 the Caithness to Moray HVDC link was re-designated as the Base Project into which the node would be incorporated. The achievable timetable for the Caithness leg with commissioning in 2016 then became the timetable for the investment.		77
77	77. 451a	Dounreay (GB)	Beauly (GB)	String a second 275kV OHL circuit on existing towers.					under construction	2012	Progresses as planned		77
77	77. 452a	Beauly (GB)	Kintore (GB)	Reconductor existing 275kV overhead line route.					design & permitting	2014	Progresses as planned (still targetting the financial year 2014/2015)		77
77	77. 453a	Blackhillock (GB)	Kincardine (GB)	Reinsulate existing 275kV route for 400kV operation and establish three new 400kV substations en-route.					design & permitting	2016	Scheduled completion in 2016 is one year later than foreseen in the 2010 TYNDP. The north of Scotland transmission system is significantly depleted by construction outages to accommodate the main Beauly-Denny rebuild by 2014. The system access that is available for this investment (453a) to accommodate a build-up of renewable generation leads to the revised completion date in 2016.		77
77	77. 455	Beauly (GB)	Denny (GB)	New double circuit 400kV OHL (220km) with new terminal substations and substation extensions en route.					under construction	2014	Progresses as planned		77
77	77. 457	Harker (GB)	Stella West (GB)	New 400kV series and shunt compensation at a number of locations across the Anglo-Scottish border.					design & permitting	2014/2015	Progresses as planned		77
78	78. 458	Hinkley (GB)	Seabank (GB)	New 60km double circuit 400kV OHL	3200	4	1					2	design & permitting	2019/20	Seabank has been delayed by three years due to corresponding delays to the associated new nuclear project.		Project needed for renewables off of the South West peninsula, the replanting of Hinkley Point nuclear power station and further CCGT at Seabank
79	79. A48	Trawsfynydd (GB)	Treudyyn (GB)	Reconductor Trawsfynydd-Treuddyn	1700	4	1					3	Planned	2017/2018	New investment in the TYNDP, as it was mistakenly omitted from the TYNDP 2010 submission. It is necessary due to RES Integration in North Wales.		Reinforcement of the internal grid to integrate the additiona flows from the RES generation.
79	79. 459	New Substation (GB)	Legacy-Shrewsbury Tee (GB)	New 400kV double circuit OHL and new 400kV substation in Mid-Wales	880					Design & Permitting	2016/2017	Progresses as planned (still targetting the financial year 2016/2017)	Investment needed to connect Mid-Wales wind farms	79
79	79. 459b	Wylfa (GB)	Pembroke (GB)	New HVDC bipolar interconnection with possible offshore connection points at the Irish Sea offshore wind farm.	2000					Planned	2020/21	Design Change – The design of the HVDC reinforcement circuit from Wylfa has changed from that in the TYNDP 2010 to now terminate at Pembroke instead of Mid-Wales. This has the potential to save some onshore consenting challenges. Additional benefits may be realised by co-ordinating the development of the offshore transmission assets with that of the onshore system. The location of the Wylfa HVDC termination may yet move offshore to be located closer to the wind turbines. The expected commissioning date has remained at 2020.		79
79	79. 460	Pentir (GB)	Trawsfynydd (GB)	Upgrage Pentir-Trawsfynydd to double circuit	3800					planned	2016/2017	Slight delay in expected commissioning date	Investment needed to accommodate new wind generation off Anglesey and nuclear replanting at Wylfa	79
79	79. 460b	Wylfa (GB)	Pentir (GB)	New 400kV Wylfa-Pentir double circuit	3600					planned	2017/2018	Progresses as planned (still targetting the financial year 2017/2018)	Investment needed to connect offshore wind and nuclear	79
80	80. 461	Woodland (IE)	Deeside (GB)	A new 260 km HVDC (200 kV DC) underground and subsea connection between Ireland and Britain with 500MW capacity. On the Irish side, a 45km direct current underground cable will be built to the Woodland substation where the VSC converter station will be placed.	500	3	2	Island of Ireland?					2	under construction	2012	Investment still on schedule for 2012, with less than 1-year delay		This medium term project will establish 500MW interconnection capacity between Ireland and GB
81	81. 462	Woodland (IE)	Turleenan (NI)	A new 140 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland.	600	3	2	NE Ireland					1	design & permitting	2016	Project delayed due to permitting process in both jurisdictions. The intermediate station Moyhill is deffered pending outcome of future load growth.		This medium term project will increase transfer capacity between Ireland and N Ireland to improve security of supply and facilitate Single Market development
82	82. 470	Bellacorick (IE)	Cashla or Flagford (IE)	New 130km single circuit 400 kV OHL from north West Mayo to the EHV system.	650	4	1					3	design & permitting	2019	Investment technical description and commisioning date are now defined, and status changed to "design and permitting".		The infrastructure development is required to facilitate connection of renewables in the North and West of the Island; It will further integrate the Ireland and N Ireland transmission systems and provide capacity for substantial demand growth in the area.
82	82. A37	tbd (NI)	Tunes Wind (NI)	North coast off-shore wind farm. Multiple connection options are under consideration.	300					under consideration	2020	New investment in TYNDP		82
82	82. 463	tbd (IE)	tbd (NI)	Strengthening of EHV networks (partial uprate and new) into Donegal and North and West of Northern Ireland and enhanced links between the two countries. Various technologies are being considered.	1500-2000					under consideration	2020	New investment in TYNDP		82
83	83. 467	Moneypoint (IE)	Kilpaddoge (IE)	A new 10km single circuit 220kV 500MVA (underground+subsea) cable constructed across the River Shannon Estuary from Moneypoint in Co. Clare to Tarbert or a new Kilpaddoge station in Co. Kerry. A new 400/220kV transformer at Moneypoint station is included in this project.	1500-2000	4	1					2	design & permitting	2014	Project delayed by 2 years because awaiting the completion of the Moneypoint 400 kV station redevelopment works to facilitate the new connection, and a delay due to foreshore permitting arising from a change in one of the connection points (from Tarbert to Kilpaddoge)		The infrastructure development is required to facilitate connection of renewables in the South of the Island; the project will also facilitate new interconnection connecting to the grid in the south.
83	83. 468	Moneypoint (IE)	North Kerry (IE)	A new 27km single 400 kV circuit, consisting of a submarine cable from Moneypoint across the Shannon Estuary and an overhead line to a new 400 kV station in north Kerry					design & permitting	2019	Investment technical description and commisioning date are now defined, and status changed to "design and permitting".	Increased capacity between the South-West and the Mid-West regions.	83
83	83. 469	Knockraha (IE)	Dunstown (IE)	A new 250km single circuit 400kV OHL from Cork to the east, with one intermediary station in the South-East.					design & permitting	2020	Investment technical description and commisioning date are now defined, and status changed to "design and permitting".	Increased capacity between Knockraha in the South-West and Dunstown in the Mid-East regions. The project will also facilate future interconnection.	83
84	84. 471	Maynooth (IE)	Woodland (IE)	A new 25km single circuit 400kv OHL from Woodland 400 kV station to a new 400 kV station near or at Maynooth 220 kV station. The project may involve upgrading existing 220 kV circuits to 400 kV or utilising the route.	1500-2000	4	1	Dublin area					2	under consideration	>2020	TYNDP 2010 investment 471 now presented in two parts (471 and IE2)		This project will provide a high capacity path around Dublin improving security of supply to the city and operability of the Dublin network
84	84. A31	Finglas / Huntstown (IE)	Woodland (IE)	A new 25km single circuit 400 kV from Woodland 400 kV station to a new 400 kV station in the vicinity of Huntstown and Finglas 220 kV stations.					under consideration	>2020	New investment in TYNDP to avoid overloads in Dublin City network and to ensure supply to north Dublin City load		84
84	84. A32	Dunstown (IE)	Maynooth (IE)	A new 40km single circuit 400kV OHL circuit from Dunstown 400 kV station to a new 400 kV station in the vicinity of Maynooth 220 kV station.					under consideration	>2020	New investment in TYNDP to avoid overloads in Dublin City network, split out from TYNDP2010 investment 471		84
84	84. A33	Carrickmines (IE)	Dunstown (IE)	A new 45km single circuit 400kV OHL from Dunstown 400 kV station to a new 400 kV station in the vicinity of Carrickmines 220 kV station.					under consideration	>2020	New investment in TYNDP to avoid overloads in Dublin City network		84
85	85. A3	F. Alentejo - Ourique - Tavira (PT)	0	New 122km double-circuit 400+150 kV OHL F. Alentejo-Ourique-Tavira. The realisation of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV, with needed extension of existing Ourique substation to include 400 kV facilities.	1390	4	1					1	planned	2018/2019	New investment in TYNDP / This project helps integrate new solar and wind power plans in Alentejo and Algarve areaNew investment in TYNDP / This project helps integrate new solar and wind power plans in Alentejo and Algarve areaNew investment in TYNDP / This project helps integrate new solar and wind power plans in Alentejo and Algarve areaNew investment in TYNDP / This project helps integrate new solar and wind power plans in Alentejo and Algarve areaNew investment in TYNDP / This project helps integrate new solar and wind power plans in Alentejo and Algarve areaNew investment in TYNDP / This project helps integrate new solar and wind power plans in Alentejo and Algarve areaNew investment in TYNDP / This project helps integrate new solar and wind power plans in Alentejo and Algarve area		This project integrates new amounts of solar (and also some wind) generation in the south of Portugal. The existing network of 150 kV is not sufficient to integrate these amounts of power and a new 400 kV axis should be launched in this region, establishing a connection between the two Southern interconnections between Portugal and Spain, the Ferreira do Alentejo-Alqueva-Brovales and Tavira-Puebla de Gusman. This axis will also close a ring of 400 kV in the Southern part of Portugal that will guarantee the load growth in the region (Algarve is one of the regions that presents the biggest growth rate in Portugal) in a safe, secure and quality way.
86	86. A49	Keadby (GB)	Grimsby West (GB)	KEAD-KILL KILL-SHBA KEAD-GRIW circuit uprate	5200	4	1					2	under consideration	long term	New investment in TYNDP	These investments are required due to unprecedented volumes of offshore wind generation connection requests.	This projects helps accommodate new offshore RES generation in the North Sea .
86	86. A50	Under Consideration (GB East Coast)	Under Consideration (GB East Coast)	Connection of Triton Knoll, Doggerbank & Hornsea GB Wind Farms and all associated works					under consideration	long term	This investment groups former 424b, 424c, 424d, 424e, 424f, 424g, 424h and 424i investments of TYNDP 2010. The group of projects on the east coast of Great Britain has been removed as work is in progress to optimise the onshore/offshore coordination and reduce potential consenting issues. Given the potential for more than 20 GW of renewable offshore generation capacity in UK waters on the East Coast it is expected that multiple connection sites will be required together with suitable circuit capacity, both onshore and offshore.		86
87	87. A53	Forsmark (SE)	Råsten (SE)	New 50km single circuit 400kV OHL	1215	2	4					2	design & permitting	2019	New investment in TYNDP		Several 400 kV AC lines and stations due to increase of nuclear power and RES, result in increased GTC
87	87. A54	Råsten (SE)	Hamra (SE)	New 85km single circuit 400kV OHL					design & permitting	2019	New investment in TYNDP		87
87	87. A55	Forsmark (SE)	Stackbo (SE)	New 70km single circuit 400kV OHL					design & permitting	2018	New investment in TYNDP		87
87	87. A56	Ängsberg (SE)	Horndal (SE)	New 55km single circuit 400kV OHL					under consideration	2020	New investment in TYNDP		87
87	87. A57	Horndal (SE)	Lindbacka (SE)	New 145km single circuit 400kV OHL					under consideration	2020	New investment in TYNDP		87
87	87. A58	Hamra (SE)	Västerås (SE)	New 50km single circuit 400kV OHL					planned	2021	New investment in TYNDP		87
87	87. 399	Vasteras (SE)	Lindbaka (SE)	Upgrade/Replacement of existing single circuit 220kV lines to 400kV.					under consideration	2021	All investments in project 87 has been prioritized and result in new commissioning dates		87
88	88. A23	offshore wind farms (FR)	several French substations (FR)	Subsea cables and substations works	3000 (MT) 6000 (LT)	4	1					3	design & permitting	2015-2020	New investment in TYNDP, required to connect offshore wind farms as decided by the French government in 2010		Connection of 6 GW offshore wind farms in 2 phases. First 3 GW phase in progress (tender).
89	89. A24	Calan (FR)	Plaine-Haute (FR)	New 100km double circuit 220kV underground cable with 2 phase shifters and T-connection of an existing HV substation; 1150 MVARs of capacitors and SVC; new transformer 400/220kV	500 MW	2	4	Brittany area					1	design & permitting	2017	New investment in TYNDP, required to secure Brittany's supply, along with DSM management plan and a new CCGT in Finistère area.		Security of supply of the Brittany
90	90. 131	Bickigen (CH)	0	Addition of a second 400/220kV transformer in an existing substation.	4000	1	2					3	design & permitting	2012	Progresses as planned		This project increase the transfer capability between FR, DE , AT towards pump storage in CH.
90	90. 132	Mühleberg (CH)	0	Construction of a new 400/220kV substation.					design & permitting	2015	Delays due to authorization process.		90
90	90. 134	Bassecourt (CH)	Romanel (CH)	Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 140km.					design & permitting	2015	Delays due to authorization process.		90
90	90. 136	Area of Bodensee (DE, AT, CH)	0	Construction of new lines, extension of existing ones anderection of 400/220/110kV-substation. / This project will increase the current power exchange capacity between the DE, AT and CH. / The project is expected to increaseNTC and Improved the security of supply. / Construction of new lines, extension of existing ones anderection of 400/220/110kV-substation. / This project will increase the current power exchange capacity between the DE, AT and CH. / The project is expected to increaseNTC and Improved the security of supply. / Construction of new lines, extension of existing ones anderection of 400/220/110kV-substation. / This project will increase the current power exchange capacity between the DE, AT and CH. / The project is expected to increaseNTC and Improved the security of supply. / Construction of new lines, extension of existing ones anderection of 400/220/110kV-substation. / This project will increase the current power exchange capacity between the DE, AT and CH. / The project is expected to increaseNTC and Improved the security of supply. / Construction of new lines, extension of existing ones anderection of 400/220/110kV-substation. / This project will increase the current power exchange capacity between the DE, AT and CH. / The project is expected to increaseNTC and Improved the security of supply. / Construction of new lines, extension of existing ones anderection of 400/220/110kV-substation. / This project will increase the current power exchange capacity between the DE, AT and CH. / The project is expected to increaseNTC and Improved the security of supply.					planned	long term	Progress as planned		90
90	90. 129	Beznau (CH)	Mettlen (CH)	Upgrade of the existing 65km double circuit 220kV OHL to 400kV.					design & permitting	2015	Progresses as planned		90
90	90. 130	La Punt (CH)	Pradella / Ova Spin (CH)	Installation of the second circuit on existing towers of a double-circuit 400kV OHL (50km).					planned	2017	Delays due to authorization process.		90
90	90. 133	Bonaduz (CH)	Mettlen (CH)	Upgrade of the existing 180km double circuit 220kV OHL into 400kV.					under consideration	2020	Progresses as planned		90
90	90. 44. 170	0	0	0					0	0	0	The investment contributes both to project 44 and project 90. For the technical description see project 44.	90
90	90. 44. 172	0	0	0					0	0	0	The investment contributes both to project 44 and project 90. For the technical description see project 44.	90
90	90. 44. 173	0	0	0					0	0	0	The investment contributes both to project 44 and project 90. For the technical description see project 44.	90
90	90. 44. 176	0	0	0					0	0	0	The investment contributes both to project 44 and project 90. For the technical description see project 44.	90
90	90. 177	Goldshöfe (DE)	Bünzwangen (DE)	A new 380kV OHL. Length: 45km.					under consideration	2020	Progresses as planned	The investment contributes also to project 45.	90
91	91. 121	Bickigen (CH)	Romanel (CH)	Construction of different new 400kV OHL sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 250km.	>4000	4	1					2	design & permitting	2015	Delays due to authorization process.		The investments help accomodating new pumping storage units which support mainly the increasing RES generation in North Sea area.
91	91. 122	Chippis (CH)	Lavorgo (CH)	Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV. Total length: 120km.					design & permitting	2017	Delays due to authorization process.		91
91	91. 123	Mettlen (CH)	Ulrichen (CH)	Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 90km.					planned	2019	Delays due to authorization process.		91
91	91. 125	Schwanden (CH)	Limmern (CH)	New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern.					design & permitting	2015	Progresses as planned		91
91	91. 126	Golbia (CH)	Robbia (CH)	New 2x 400kV cable connection between Golbia and the Bernina line double circuit.					under consideration	2019	Progresses as planned		91
91	91. 127	Magadino (CH)	Verzasca (CH)	Upgrade of existing 150kV line into 220kV line.					under consideration	2020	Progresses as planned		91
91	91. 128	Bâtiaz (CH)	Nant de Drance (CH)	New 400kV double circuit OHL between Bâtiaz and Châtelard. New 2x 400kV cable connection between Châtelard and Nant de Drance. Total length: 22km.					design & permitting	2016	Delays due to authorization process.		91
92	92. 146	Aachen/Düren region (DE)	Lixhe (BE)	Connection between Germany and Belgium including new 100km HVDC underground cable and extension of existing 380kV-substations. On Belgian side, new 380 kV circuit between Lixhe and Herderen and second 380 kV overheadline in/out from Herderen to Lixhe. In Belgium, addition of 2 transformers 380/150 kV in Lixhe and in Limburg part;	1000	3	2	Northern Belgium					2	design & permitting	2017	Project entered design and permitting phase in 2011, technical description has been completed and expected date of comissioning is 2017	Alegro Project	First Belgium-Germany interconnection. This project enhances security of supply of both BE and DE. This HVDC link in an AC grid brings flexibility and bidirectional power control allowing integration of RES in both countries. This project aims to be a demonstration for HVDC link integration in the AC meshed grid.
93	93. 413	Ørskog (NO)	Fardal (NO)	New 285 km single circuit 400kV OHL.	2250	3	3	South west of Trondheim (county Møre and Romsdal)					3	under construction	2015	Investment delayed due to due to long permitting procedure.	The project is key to improve SoS in Mid-Norway: presently, for several N-1 contingencies, load might be disconnected. The project is also the pre-requisite to lift the ban on RES developement in the whole area covered by the new line Ørskog - Fardal.	Security of supply for mid-Norway (Møre and Romsdal mainly) and RES integration in western Norway.
93	93. 398A	Under consideration (SE)	0	New shunt compensation of OHL.					under consideration	2015	New part of investment 398 in TYNDP 2010	Investment 398 in TYNDP 2010 have been divided into 398A and 398B. 398B is described in project 104.	93
93	93. 403	Scandinavia north (SE)	Scandinavia South (SE)	A joint Stattnett & Svenska Kraftnat study north - south reinforcement (AC or VSC), expected length: 400 - 500km under study.					under consideration	2025	Postponed after reprioritization of the project portfolio		93
93	93. 414	Fardal (NO)	Aurland (NO)	Voltage upgrading of existing single circuit 300kV OHL Fardal-Aurland Extension of 413 - Ørskog - Fardal.					planned	2020	Investment postponed, especially because of long permitting processes.		93
93	93. 417	Aura/Viklandet (NO)	Fåberg (NO)	Voltage upgrading of existing single circuit 300kV OHL Aura/Viklandet-Fåberg.					under consideration	long term	Investment postponed, especially because of long permitting processes.		93
93	93. 416	Klæbu (NO)	Aura/ Viklandet (NO)	Voltage upgrading of existing single circuit 300kV OHL Klæbu-Aura.					design & permitting	2018 (2016-2020)	Investment postponed, especially because of long permitting processes.		93
94	94. 139	Vierraden (DE)	Krajnik (PL)	Upgrade of existing 220 kV line Vierraden-Krajnik to double circuit 400 kV OHL.	>1000	1	2					1	design & permitting	long term	Expected date of commissioning was adjusted due to long permitting process and strong local public resistance.		PSTs – Control of the transits of power on the polish synchronous profile (increase of import capacity, increase of grid operation safety).
94	94. A68	Krajnik (PL)	0	Upgrade 400 kV					design & permitting	2014	New investment in the TYNDP, split out from investment 139		94
94	94. A69	Mikułowa (PL)	0	Upgrade 400 kV					design & permitting	2014	New investment in the TYNDP, split out from investment 139		94
94	94. A70	Krajnik (PL)	0	New PST					design & permitting	2014	New investment in the TYNDP, split out from investment 139		94
94	94. A71	Mikułowa (PL)	0	New PST					design & permitting	2014	New investment in the TYNDP, split out from investment 139		94
95	95. A119	Dobrudja(BG)	Burgas (BG)	New 140km single circuit 400kV OHL in parallel to the existing one.	1500	4	3					1	planned	2016	New investment in TYNDP, required to accommodate 2000MW RES in Dobrudja region		It contributes to the accomodation of large amount of RES in Dobrudja region (2000 MW). It also contributes to North-South transfers and increases the SoS in Burgas region.
95	95. 265	Vidno (BG)	Svoboda (BG)	New 400kV double circuit OHL to accommodate 2000 MW RES generation in N-E Bulgaria (Dobruja region). Line length: 2x70km.					planned	2015	Moved from LT(TYNDP 2010) to MT due to high interest for very fast implementation of about 2000MW RES generation in Dobrudja region		95
95	95. 263	SS 400/110kV Svoboda(Krusari)	0	New 400/110kV substation to accommodate the expected RES generation(2000MW) in N-E Bulgaria (Dobruja region)					planned	2015			95
95	95. 264	SS 400/110kV Vidno	0	New 400/110kV substation to accommodate the expected RES generation(2000MW) in N-E Bulgaria (Dobruja region)					planned	2015			95
95	95. 266	IN-OUT in Svoboda on actual 400kV OHL Isaccea(RO)-Varna (BG)	0	New 400kV double circuit OHL to accommodate the expected RES generation(2000MW) in N-E Bulgaria (Dobruja region). Line length: 2x10km.					planned	2015			95
96	96. A64	Keminmaa (FI)	Pyhänselkä (FI)	Integration of new generation + increased transmission capacity demand.	1000	4	1					1	under consideration	2019	New investment in TYNDP, split out from investment 393, and now been moved as a stand-alone project cluster because of his specific benefits.		Integration of new generation and increased transmission capacity demand.
97	97. A65	Uusnivala (FI)	Pyhäjoki (FI)	New double circuit 400 kV OHLs	1600	4	5					1	under consideration	2020	New investment in TYNDP, required to connect Fennovoimas new 1 250-1 700 MW nuclear power plant that will be built in Pyhäjoki		New investment in TYNDP, required to connect Fennovoimas new 1 250-1 700 MW nuclear power plant that will be built in Pyhäjoki
98	98. A66	Rauma (FI)	Forssa (FI) / Lieto (FI) / Ulvila (FI)Forssa (FI) / Lieto (FI) / Ulvila (FI)Forssa (FI) / Lieto (FI) / Ulvila (FI)Forssa (FI) / Lieto (FI) / Ulvila (FI)	New single circuit 400 kV OHLs	1600	4	5					1	under consideration	2020	New investment in TYNDP, required to connect TVO's new 1 000-1 800 MW nuclear power plant that will be built in Olkiluoto.		New investment in TYNDP, required to connect TVO's new 1 000-1 800 MW nuclear power plant that will be built in Olkiluoto
99	99. 324	Dobrzeń (PL)	Wrocław/ Pasikurowice (PL)	New 76 km 400kV 2x1870 MVA OHL double circuit line from Dobrzeń to splitted Pasikurowice - Wrocław line + upgrade and extension of 400 kV switchgear in substation Dobrzeń.	1800	4	5	Warsaw and lower Silesia area					1	design & permitting	2017	Progresses globally as planned. Technical description and commissioning date have been updated so as to deliver full benefit as from 2017		Dobrzeń - the project introduces new infrastructure (2x400 kV line) to allow power evacuation from two (2x9000 MW) conventional units to be installed in existing power plant Opole. The new line provides power supply for agglomeration Wroclaw, it increases the SoS for this area.
100	100. 335	Ostrołęka (PL)	Olsztyn Mątki (PL)	New 138km 400kV 2x1870 MVA double circuit OHL line Ostrołęka - Olsztyn Mątki after dismantling of 220kV line Ostrołęka - Olsztyn with one circuit from Ostrołęka to Olsztyn temporarily on 220kV.	1000	4	5					1	design & permitting	2017	The time schedule of the project was shifted to meet the schedule of the generation connection.		Ostrołęka - the new 400 kV line allows power evacuation from new 1000 MW conventional unit to be installed in existing power plant Ostroleka.
101	101. 327	Kozienice (PL)	Ołtarzew (PL)	New 130km 400kV 2x1870 MVA OHL double circuit line Kozienice - Ołtarzew + upgrade and extension of 400 kV switchgear in substation Kozienice for the connetion of new line	1000	4	5	Warsaw area					1	design & permitting	2017	The time schedule of the project was shifted to meet the schedule of the generation connection.		Kozienice - the new 2x400 kV line allows power evacuation from new 1000 MW conventional unit to be installed in existing power plant Kozienice. The new unit is foreseen to supply Warsaw agglomeration area. The project also allows to close the 400 kV ring around Warsaw agglomeration are increasing the SoS significantly.
101	101. 338	Kozienice (PL)	Mory/ Piaseczno (PL)	Replacement of conductors (high temperature conductors).					under construction	2014	Progresses as planned, with commissioning now expected in 2014		101
102	102. A72	Gdańsk Błonia (PL)	0	Extension and upgrade of an existing 400/110 kV susbstation Gdańsk Błonia for connection of planned 900 MW power plant.	2900	4	5					2	planned	2020	New investment in TYNDP	Power Evacuation North. The upgraded substation will connect a planned 900 MW CCPP.	North - the North-South corridor provides necessary capacity to evacuate the power from new 2900 MW of conventional generation planned to be installed in northern Poland.
102	102. 334	Pątnów (PL)	Grudziądz (PL)	New 174km 400kV 2x1870 MVA double circuit OHL line Pątnów - Grudziądz after dismantling of 220kV line Pątnów - Jasiniec (two parallel lines) and Jasiniec - Grudziądz. One circuit from Pątnów to Grudziądz via Jasiniec temporarily on 220kV.					design & permitting	2020	The time schedule of the project was shifted to meet the schedule of the generation connection.	Power Evacuation North	102
102	102. 326	Grudziądz (PL)	Gdańsk Przyjaźń (PL)	A new AC 400/110kV substation between existing substation Grudziądz and planned substation Gdańsk Przyjaźń. New substation Pelplin is connected by new 110km 400kV 2x1870 MVA OHL double circuit lines Grudziądz - Pelplin and Pelplin - Gdańsk Przyjaźń after dismantling of 220kV line Jasiniec - Gdańsk.					planned	2020	The time schedule of the project was shifted to meet the schedule of the generation connection.	Power Evacuation North	102
103	103. 145	Niederrhein (DE)	Doetinchem (NL)	New 400kV line double circuit DE-NL interconnection line. Length:60km.	13900	3	1	NW part of Netherlands					3	design & permitting	>=2013	Delays due to authorization process.		The project reinforces the Dutch grid to accommodate new conventional and renewable generation, to handle new flow patterns and to increase the interconnection capacity between DE and NL"
103	103. 438	Eemshaven (NL)	Diemen (NL)	New 175-200km AC overhead line with capacity of 2x2650 MVA of 380kV.					design & permitting	2018	Delays due to authorization process.		103
103	103. 439	Borssele (NL)	Geertruidenberg (NL)	New 100-130km double-circuit 380kV OHL with 2x2650 MVA capacity.					design & permitting	2016	Delays due to authorization process.		103
103	103. 440	Maasvlakte (NL)	Beverwijk (NL)	New 380 kV double-circuit mixed project (OHL+ underground cable) including approximately 20km of underground cable for 2650 MVA. The cable sections are a pilot project. The total length of cable at 380kV is frozen until more experience is gained.					under construction	2016	Delays due to authorization process.		103
103	103. 441	Zwolle (NL)	Hengelo (NL)	Upgrade of the capacity of the existing 60km double circuit 380kV OHL to reach a capacity of 2x2650 MVA.					under consideration	long term	Progresses as planned		103
103	103. 442	Krimpen aan de Ijssel (NL)	Maasbracht (NL)	Upgrade of the capacity of the existing 150km double circuit 380kV OHL to reach a capacity of 2x2650 MVA.					under consideration	long term	Progresses as planned		103
104	104. 398B	Under consideration (SE)	0	New series compensation of OHL.	1200	2	1					2	under consideration	2015	In the 2010 TYNDP only series compensation was a part of the investment. The series compensation contributes to project 104 and the shunt compensation to project 93. Therefor I don’t think that the row in the table for 93.104.398 should be blank.	Investment 398 in TYNDP 2010 have been divided into 398A and 398B. 398A is described in project 93.	RES integration in mid-Norway (Trøndelag and Nordland) and reinforcement of Swedish internal interconnections in order to facilitate wind power integration in northern Sweden
104	104. 415	Namsos (NO)	Klæbu and Storeheia (NO)	New line and voltage upgrade of 286km single circuit 400kV OHL					design & permitting	2015	Delays due to authorization process.	New line and voltage upgrade to facilitate new wind power generation	104
104	104. 418	Nedre Røssåga (NO)	Namsos (NO)	Upgrade of 70km single circuit 400kV OHL					design & permitting	2019	Investment postponed, especially because of long permitting processes.	Increased capasity between north and mid Norway. Facilitates RES integration	104
104	104. 420	Storheia (NO)	Orkdal / Trollheim (NO)	New 130km single circuit 400kV OHL					design & permitting	2017-2020	Investment postponed due to long permitting procedure.	New line to facilitate wind power generation	104
104	104. A59	Råbäcken (SE)	Letsi - Betåsen (SE)	New 55km single circuit 400kV OHL					under consideration	2017	New investment in TYNDP. Will probably be postponed after 2020 due to later development of wind power in the area		104
104	104. A51	Svartisen (NO)	Nedre Røssåga (NO)	New 116km 400kV OHL					planned	2020	New investment in TYNDP	New line to facilitate wind power generation	104
105	105. A60	Skogssäter (SE)	Stenungsund/Stenkullen (SE)	New 80km single circuit 400kV OHL	600	2	1					1	under consideration	2019	New investment in TYNDP		This project facilitates the connection of wind power along the Swedish west coast
106	106. A34	tbd (IE)	tbd (GB)	A new HVDC subsea connection between Ireland and Great Britain	700	3	2					2	under consideration	long term	New investment in TYNDP, conceptual, cost benefit analysis to be confirmed		This project will increase interconnection capacity between Ireland and Great Britain
107	107. A25	tbd (IE)	tbd (FR)	A new HVDC subsea connection between Ireland and France	700	3	2					3	under consideration	long term	New investment in TYNDP, conceptual, cost benefit analysis to be confirmed		This project will establish interconnection capacity between Ireland and France
108	108. A134	Tarnita (RO)	Mintia (RO)	New 145km double circuit 400kV OHL	1000	4	1					1	planned	2018	New investment in TYNDP	Connection of pumped storage hydro plant Tarnita Lapustesti to the grid. The plant has an installed capacity of 1000 MW and will support system balancing, especially in order to face the intermittent RES output.	The project will connect to the grid 1000MW hydro pump storage.
108	108. A135	Tarnita (RO)	Cluj E - Gadalin (RO)	New 40km double circuit 400kV OHL					planned	2018	New investment in TYNDP		108
108	108. A136	Tarnita (RO)	0	New 400kV substation					planned	2018	New investment in TYNDP		108
109	109. A35	Oriel (IE)	Oriel Wind Farm (IE)	Oriel off-shore wind farm connecting to a new Oriel 220 kV station located on the Louth - Woodland 220 kV circuit	330	4	1					2	under consideration	2016	New investment in TYNDP, required to connect Offshore Wind		This project will facilitate the connection of offshore wind
109	109. A36	Carrickmines (IE)	Kish Bank Wind Farm (IE)	Kish Bank off-shore wind farm connecting to the existing Carrickmines 220 kV station	364					under consideration	2015	New investment in TYNDP, required to connect Offshore Wind		109
109	109. A38	Northern Ireland (NI)	East Coast Offshore (IE)	'East Coast Off-shore' wind farm connecting to a 275 kV station to be determined. Multiple connection options are under consideration.	300-600					under consideration	2018	New investment in TYNDP, required to connect Offshore Wind		109
110	110. 424	Kvilldal (NO)	tbd (GB)	A new 1000MW HVDC bipolar installation connecting Western Norway and Great Britain via 800km subsea cable; DC voltage is to be determined.	1000-1400	1	2					3	design & permitting	2018/2021	Capacity revised. Investment postponed, especially because of long permitting processes.		Market integration. Facilitate RES integration in southern and western Norway and improve security of supply.
111	111. 396	Finland North (FI)	Sweden North (SE)	Third single circuit 400kV AC OHL between Sweden and Finland. Expected capacity: 1850 MVA.	700	3	2					1	under consideration	2021	The projects reinforcing the North-South transmission in the Scandinavia have been prioritised ahead of this project. Based on common estimation project can be delayed to 2021. SvK will evaluate the project and the timetable in ongoing studies		Third AC 400 kV crossborder line between North-Sweden and North-Finland is under consideration. Strenghtening the AC connection between Finland and Sweden is necessary due to new wind power generation, larger conventional units and decommissioning of the existing 220 kV interconnector.
112	112. 98	Pordenone (IT)	0	Voltage upgrade of the existing Pordenone 220kV substation up to 400kV. The substation will be connected in and out to the existing Udine O. – Cordignano 400kV line.	2150	2	5	Triveneto area					1	planned	long term	Progresses as planned		This projects hepls to increase the security of supply in the N-E part of Italy.
112	112. 105	Treviso (IT)	0	New 380/132kV substation in Treviso area, connected in and out to the existing 380kV line “Sandrigo - Cordignano".					design & permitting	mid term	Project delayed by 2 years due to longer than expected permitting procedure.		112
112	112. 106	Schio (IT)	0	New 220/132kV substation in Schio area, providing the connection in and out to the existing 220kV line "Ala-Vicenza Monte Viale”.					planned	mid term	Project delayed by 2 years due to longer than expected permitting procedure.		112
112	112. 107	Vicenza Industrial (IT)	0	New 380/132kV substation in the industrial area of Vicenza, connected in and out to the existing Sandrigo-Dugale 400kV line.					planned	long term	Progresses as planned		112
112	112. 108	North West Padova (IT)	0	New 220/132kV substation in North West Padova area, complying with 400kV standards, providing the connection in and out to the existing Dugale-Marghera Substation1 220kV line.					planned	long term	Progresses as planned		112